## Read Me
Overview
The purpose of this workbook is to identify assumptions for construction of the Ballona Wetlands Project. The assumptions will be used to support the air quality, greenhouse gas, and transportation analyses. The workbook includes three primary tabs, which are denoted in dark blue. The light blue tabs summarize the construction sequences for Alternatives 1a through 6.
Instructions for Review
The dark blue tabs should be reviewed in detail and used to provide the construction assumptions. Below is a brief description of each tab.
1) Construction Master (Alt 1): This tab summarizes the construction sequence for Alternative 1 (columns A through D) and identifies the requested construction data (columns E through O). Information on construction activities was obtained from Appendix 3F. Specific instructions for each requested data are provided in drop down boxes, which can be viewed by clicking the column title (e.g., click “start date” to reveal instructions for completing column E). The data entry fields are blank for all sequences except Sequence 2b, Construct Ecology Center and new ball fields. Assumptions for construction of Sequence 2b were developed using CalEEMod default values for the anticipated land use types (46,000 square foot Urban Ecology Center and 4 baseball fields).
2) Equipment Ref: Since many of the actions are similar (e.g., “remove trash”), it is anticipated that the same (or similar) equipment and personnel assumptions can be used for multiple actions. The Equipment Ref tab should be used to identify equipment and personnel assumptions that can be used to evaluate similar construction activities. Specific instructions for each requested data are provided in drop down boxes, which can be viewed by clicking the column title. Equipment and personnel assumptions for Sequence 2b have been added based on CalEEMod defaults.
3) Soil Export: This tab summarizes the options for exporting excess soil offsite during Sequence 19b, Export fill to Area C North and offsite. Some data have been inserted based on information obtained from Appendix 3H. Please provide the remaining information by completing the blank cells.
The light blue tabs identify the construction sequences for Alternatives 1a through 6. Differences relative to Alternative 1 are identified in Column E. Construction assumptions developed for Alternative 1 will be used to evaluate sequences that are the same as Alternative 1 (unless otherwise instructed). Please confirm this approach and/or provide alternative assumptions, as appropriate.
Next Steps
ICF requests Psomas review and provide the requested construction data, as available. ICF can participate in a conference call with Psomas to discuss the information further. Assumptions specific to employee vehicle trips and haul truck trips will be coordinated with Raju Associates to ensure consistency between the air quality and transportation analyses.

## Construction Master (Alt 1)
Sequence | Area | Title | Actions | Start Date | Working Days | Overlap | Equipment Reference | Haul Trucks |  |  | Acres Paved | Acres Graded | Concrete Poured (CY) | SF Demolished | Notes/ Assumptions
[8 empty] | Trips per day | Miles per trip | Total Trips
PHASE 1
1 | B | Area "B" Southeast Gas Lines | 1a. Remove and relocate existing gas line | 2017-01-02 | 20 | A | 4 | [7 empty] | Assumed start date. Schedule shift as required after EIR certification and governmental approvals..
2 | B | Area "B" South Enhancement | 2a. Create swale (10,000 CY wet cut) | 2017-01-02 | 40 | A | 1 | [7 empty] | Independent Seqence which may occur any time during the project schedule .
3 | A | Area "A' Gas Line Removal | 3a. Remove existing inactive gas line | 2017-01-02 | 10 | A | 4 | [8 empty] | Color | Description
|  |  | 3b. Cut and cap gas line at Fiji Way | 2017-01-02 | 1 | A | 4 | [9 empty] | Could start sooner if desired, not later
4 | A & B | Pedestrian/Bike Bridge | 4a. Construct temporary & portion of final re-routed trail to existing trail | 2017-04-17 | 40 | A, B, C | 7 | [7 empty] | 2nd step, start after rainy season |  | Work must start and finish in non-rainy season
|  |  | 4b. Construct new pedestrian/bike bridge over Ballona Creek | 2017-01-02 | 130 | A, B, C | 8 | [7 empty] | 1st step, start on south side |  | Cannot start until habitat establishment period complete. Work in Non-rainy season
|  |  | 4c. Reroute Ballona Creek Bike Trail under Culver Blvd Bridge | 2017-07-04 | 5 | A, B, C | 7 | [7 empty] | Final step weekend after the 4th of July |  | Independent effort, can start any time after this start date.
5 | A & C | Lincoln Bridge | 5a. Build Lincoln Bridge next to Culver Bridge to connect Area A to Area C North | 2017-07-04 | 65 | A, B, C | 9 | [7 empty] | Note, if assuming new bridge NOT using existing foundations, Use Equip 8 and 130 days duration
6 | A | Clear, Grub, and Stockpile Area "A" | 6a. Remove vegetation from Area A (54,400 CY dry cut) | 2017-07-04 | 10 | C | 10
|  |  | 6b. Remove trash | 2017-07-04 | 20 | C | 10
|  |  | 6c. Stockpile | 2017-07-04 | 20 | C | 10
7 | A | Excavate Area "A" | 7a. Remove 36" concrete pipe near center of Area A | 2017-07-04 | 5 | C | 4
|  |  | 7b. Excavate old fill from Area A (1,134,200 CY wet cut and 54,400 dry cut, see note) | 2017-07-04 | 555 | C | 11 | [7 empty] | This cut is the 2.05M CY, less cuts accounted for in other sequences. Assume dry max move is 10k cy/day; wet max move is 4k cy/day; wet soil spread over 4 of 20 acre for 5 days is limiting issue.
|  |  | 7c. Dig below (over excavate) future levees (25,200 CY dry cut) | 2017-07-04 | 5 | C | 11 | [7 empty] | Within Seq 7b
8 | A | Area "A' Construct North Levee | 8a. Grade and construct new levee around Area A (125,300 CY fill) | 2017-07-04 | 35 | C | 12 | [7 empty] | Within Seq 7b
|  |  | 8b. Protect Del Ray 13, 14, 15, 17, and 19 | 2017-01-02 | n/a | n/a | n/a
9 | B & Property 1 | Area "B" North Gas Line Relocation & Well Abandonment | 9a. Drill new well at SoCal Gas Plant to replace Del Ray 12 | 2017-01-02 | 50 | D | 5
|  |  | 9b. Abandon and plug Del Ray 12 | 2017-04-03 | 90 | D | 6
|  |  | 9c. Remove/relocate existing pipelines | 2017-07-04 | 10 | D | 4
10 | B | Area "B" North Clear & Grub | 10a. Remove vegetation from Area B North and interim levee (25,000 CY wet cut) | 2017-07-04 | 10 | E | 10
|  |  | 10b. Remove trash | 2017-07-04 | 50 | E | 10
11 | B | Area "B" North Over-Excavate and Stockpile | 11a. Excavate Area B North (56,700 CY wet cut) | 2017-07-04 | 25 | E | 11
|  |  | 11b. Dig below (over excavate) future levees (11,400k CY wet cut) | 2017-07-04 | 5 | E | 11
12 | B | Construct Area "B" Levee | 12a. Construct Area B levees (452,800 CY fill = total import from Area A = 566,000 CY) | 2017-08-14 | 165 | E | 12 | [7 empty] | Uses dry or dried out dirt from Area A, imported over new Ballona bridge. Area A exported dirt placed here first. Time is within 555 days from Seq 7, but extra equipment added during this time.
13 | B | Clear, Grub, and Stockpile Area "B" East | 13a. Remove vegetation in Area B East (4,600 CY wet cut) | 2018-02-05 | 5 | E | 1
|  |  | 13b. Stockpile and prepare for fill | 2018-02-05 | 5 | E | 10
14 | B | Area "B" East Stockpile Grading | 14a. Grade Area B east and import from Area A (80,000 CY import from Area A) | 2018-02-12 | 25 | E | 11 | [7 empty] | Uses dry or dried out dirt from Area A, imported over new Ballona bridge. Area A exported dirt placed here second. Time is within 555 days from Seq 7, but extra equipment added during this time.
15 | C | Clear & Grub Area "C" North & South | 15a. Protect baseball fields and structures. | 2017-01-02 | n/a | n/a | n/a
|  |  | 15b. Clear vegetation from Area C North (56,000 CY dry cut) & South (15,000 CY dry cut) | 2018-04-02 | 10 | C, E | 10
|  |  | 15c. Re-align and replace Marina ditch (45,000 CY wet cut) | 2018-04-23 | 15 | C, E | 11
16 | A & C | Area "A" Grading and Export to Area "C" North & South | 16a. Excavate Area A and export to C South (300,000 CY total) | 2018-05-21 | 75 | C, E | 11 | [7 empty] | Uses dry or dried out dirt from Area A, imported over new Lincoln bridge and across Culver Blvd. Area A exported dirt placed here third. Time is within 555 days from Seq 7, but extra equipment added during this time.
|  |  | 16b. Excavate Area A and export to C North (720,000 CY ultimate total; 420,000 CY to C North) | 2018-09-03 | 110 | C, E | 11 | [7 empty] | Uses dry or dried out dirt from Area A, imported over new Lincoln bridge. Area A exported dirt placed here fourth. Time is within 555 days from Seq 7, but extra equipment added during this time.
17 | C | Finish Grading for Uplands Area "C" South | 17a. Finish grading Area C South | 2019-06-03 | 15 | C, E | 13
|  |  | 17b. Re-establish upland vegetation | 2019-06-24 | 5 | C, E | 14
18 | B | Area "B" New and Reconstructed Culverts | 18a. Install culverts under Culver/Jefferson Blvd, Gas Co Rd, and FWM berm; modify existing culvert under west end of Culver Blvd. | 2019-01-07 | 130 | F | 1
|  |  | 18b. Remove existing FWM pipes and outlets | 2019-07-08 | 15 | F | 1
|  |  | 18c. Construct new FWM outlet and spillway | 2019-07-29 | 40 | F | 1
19 | A & B | Area "A" and Area "B" North Excavate and Breach Existing Levees | 19a. Excavate Ballona Creek Channel in Areas A and B North (277,800 CY cut) | 2019-04-15 | 130 | G | 11 | [7 empty] | Total time allowed during non-rainy season - 4/15 to 10/15
20 | A & B | Area "A" and Area "B" North Block and Fill Existing Channels | 20a. Install temporary pipe | 2019-04-15 | 10 | G | 4 | [7 empty] | Time assumed within Seq 19
|  |  | 20b. Temporary block then fill existing Ballona Creek (269,100 CY fill from Seq 19) | 2019-04-15 | 60 | G | 11 | [7 empty] | Time assumed within Seq 19
21 | A & B | Area "A" and Area "B" North Remove Existing Levees | 21a. Remove old Ballona Creek levee (424,400CY) and excavate new channel meanders - Export to Area C North, quantities included in Sequence 16, ultimate. | 2019-07-08 | 120 | G | 11 | [7 empty] | Time assumed within Seq 19
22 | B | Area "B" West Fire Access Road | 22a. Construct maintenance and fire road in Area B West | 2019-10-14 | 20 | H | 7
|  |  | 22b. Reconstruct Area B parking lot | 2019-10-14 | 20 | I | 7
23 | A & B | Bike Path, Pedestrian Walkway and Amenities | 23a. Construct bike and ped trails on levees | 2019-10-14 | 65 | J | 7
|  |  | 23b. Construct County Parking Structure Foundation | 2019-10-14 | 60 | K | 2 | [7 empty] | Independent sequence anytime after Seq 8a. Is complete
|  |  | 23c. Construct County Parking Structure | 2019-10-14 | 120 | K | 3 | [7 empty] | Independent sequence anytime after Seq 8a. Is complete
24 | A | Export | 24a. Export final excess dirt quantity (Assume up to 110,000 CY) | 2019-10-14 | 35 | C, E | 15 | [7 empty] | See separate tab for export
PHASE 2
Area A Gas Well Removal and Restoration
25 | A & Property 1 | Gas Well Abandonment | 25a. Drill new well at SoCal Gas Plant to replace Del Ray 19 | 2017-01-02 | 50 | L | 5 | [7 empty] | Assumes one crew working sequencially. Multiple crews could cut time down.
|  |  | 25b. Abandon and plug Del Ray 13, 14, 15, 17, 18, and 19 | 2017-03-13 | 225 | L | 6 | [7 empty] | Assumes one crew working sequencially. Multiple crews could cut time down.
|  |  | 25c. Remove existing gas lines serving removed wells | 2018-01-22 | 10 | L | 4
26 | A | Area A around Wells Clear & Grub | 26a. Remove vegetation around wells (2,000 CY) | 2018-01-22 | 5 | M | 1
27 | A | Area A around Wells Grading and Export to West Area B | 27a. Excavate Area A and Export to West Area B (208,000 CY) | 2018-01-22 | 5 | M | 11
28 | A | Finish Grading For Uplands | 28a. Finish grading around wells | 2018-02-12 | 10 | M | 1
|  |  | 28b. Re-establish upland vegetation | 2018-02-26 | 5 | M | 14
Area B wells
29 | B | Area B Abandon Wells | 29a. Drill new well at SoCal Gas Plant to replace Del Rey 9 and Vidor 18 | 2017-01-02 | 50 | N | 5 | [7 empty] | Assumes one crew working sequencially. Multiple crews could cut time down.
|  |  | 29b. Abandon and plug Vidor 1, 2, 3, 5, 14, 18 and Del Rey 4, 5, 9, 11 | 2017-03-13 | 225 | N | 6 | [7 empty] | Assumes one crew working sequencially. Multiple crews could cut time down.
|  |  | 29c. Remove existing pipelines | 2017-11-13 | 10 | N | 4
30 | B | Area B around Wells Clear & Grub | 30a. Remove vegetation around wells (2,000 CY) | 2017-11-27 | 5 | O | 1
31 | B | Finish Grading For Uplands | 31a. Finish grading around wells | 2017-12-04 | 10 | O | 1
|  |  | 31b. Re-establish upland vegetation | 2017-12-18 | 5 | O | 14
Area B West
32 | B | Area "B" West Clear & Grub | 32a. Remove vegetation in Area B West (76,000 CY) | 2023-04-17 | 10 | P | 10
33 | B | Area "B" West Grading and Levee Extention | 33a. Install temporary flexible storm drain | 2023-05-01 | 10 | P | 1
|  |  | 33b. Dig below (over excavate) levees (10,800k CY wet cut) | 2023-05-01 | 10 | P | 12
|  |  | 33c. Grade Area B West channels, construct salt pan berm, and construct levee with import from stockpile from Area B North and East at 248,000 CY (31,200 + 216,800 CY (291,800 less 49,000 and 26,000)) | 2023-05-15 | 75 | P | 12
34 | B | Area "B" West Excavate and Breach Existing Levees | 34a. Breach existing levee in Area B West and place in Stability berms (75,000 CY wet = 26,000 + 49,000) | 2023-04-15 | 130 | P | 11 | [7 empty] | Time allowed during non-rainy season = 130 Days, Time expected = 30
35 | B | Finish Bike Path, Pedestrian Walkway and Amenities | 35a. Construct maintenance and fire access road and bike path on new levee. | 2023-08-14 | 20 | Q | 7
36 | B | Finish Grading For Uplands | 36a. Finish grading Area B East | 2023-09-04 | 10 | Q | 13
|  |  | 36b. Re-establish upland vegetation | 2023-09-18 | 5 | Q | 14
Sources: Appendix F - Construction Sequencing.pdf; Appendix_3F.pdf
Restoration Schedule: 2017-2035
Note on D27: Nick Garrity: 344,500+92,500=437,000
Note on D43: Nick Garrity: 156,100+113,000
Note on D44: Nick Garrity: Please provide backup for this quantity - not sure where it comes from and if it double conts 19a.

## Equipment Ref
NOTES:
Reference # | Action(s) | Equipment Type | Number per day | Hours per day | Employees per day |  | Crane
1 | 2a, 13a, 18a, 18b, 18c, 26a, 28a, 30a, 31a, 33a | Grader | 2 | 8 | 26 |  | Forklift
|  | Truck | 12 | 8 |  | Minor clearing, grading, etc | Generator Set
|  | Loader | 4 | 8 |  |  | Tractors/Loaders/Backhoe
|  | Backhoe | 2 | 8 |  |  | Welder
|  | Generator Set | 1 | 8 |  |  | Grader
2 | 23b | Grader | 4 | 8 | 24 |  | Drill Rig
|  | Truck | 10 | 8
|  | Loader | 4 | 8
|  | Backhoe | 1 | 8 |  | Building foundation
|  | Drill Rig | 1 | 8
|  | Generator Set | 2 | 8
3 | 23c | Truck | 12 | 8 | 40
|  | Backhoe | 1 | 8
|  | Crane | 1 | 8
|  | Loader | 4 | 8 |  | Buildings
|  | Generator Set | 2 | 8
4 | 1a, 3a, 3b, 7a, 9c, 20a, 25c, 29c | Backhoe | 1 | 8 | 8
|  | Truck | 4 | 8
|  | Loader | 1 | 8
|  | Grader | 1 | 8 |  | Gas and Pipe Removals
5 | 9a, 25a, 29a | Drill Rig | 1 | 24 | 70
|  | Generator Set | 6 | 24
|  | Truck | 20 | 24
|  | Forklift | 1 | 24
|  | Backhoe | 1 | 24 |  | Drill New Wells
|  | Crane | 2 | 24
6 | 9b, 25b, 29b | Drill Rig | 1 | 12 | 17
|  | Truck | 17 | 12
|  | Generator Set | 1 | 12
Abandon Wells
7 | 4a, 4c, 22a, 22b, 23a, 35a | Backhoe | 2 | 8 | 15
|  | Truck | 10 | 8
|  | Loader | 4 | 8
|  | Grader | 1 | 8
Paved Trails/Lots
8 | 4b (5a?) | Drill Rig | 1 | 8 | 50
|  | Crane | 2 | 8
|  | Generator Set | 4 | 8
|  | Truck | 30 | 8
|  | Forklift | 2 | 8 |  | New Bridge
|  | Backhoe | 2 | 8
|  | Grader | 1 | 8
9 | 5a | Drill Rig | 1 | 8 | 30
|  | Crane | 2 | 8
|  | Generator Set | 3 | 8
|  | Truck | 16 | 8
|  | Forklift | 2 | 8 |  | Temp Linc Bridge
10 | 6a, 6b, 6c, 10a, 10b, 13b, 15b, 32a | Grader | 4 | 8 | 35
|  | Truck | 20 | 8
|  | Loader | 8 | 8
|  | Backhoe | 2 | 8
|  | Generator Set | 1 | 8 |  | Major Clearing
11 | 7b, 7c, 11a, 11b, 14a, 15c, 16a, 16b, 19a, 20b, 21a, 27a, 34a | Grader | 6 | 8 | 80
|  | Truck | 50 | 8
|  | Loader | 6 | 8
|  | Backhoe | 6 | 8 |  | Excavation
12 | 8a, 12a, 33b, 33c | Grader | 6 | 8 | 90
|  | Truck | 60 | 8
|  | Loader | 6 | 8
|  | Backhoe | 6 | 8 |  | Levee construction
|  | Drill Rig | 1 | 8
|  | Generator Set | 2 | 8
13 | 17a, 36a | Grader | 4 | 8 | 10
|  | Truck | 240 | 8
Finish Grading
14 | 17b, 28b, 31b, 36b | Truck | 10 | 8 | 16
Planting
15 | 24a | Loader | 2 | 8 | 122
|  | Truck | 120 | 8
Truck Export
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40

## Soil Export Alt1
After grading operations are complete, there may be up to 110,000 c.y. of excess soil that might be exported outside the project boundary for disposal. Export will occur during Sequence 24.
Option | Description | Haul Trucks |  |  | Crane |  |  | Tugs (to pull barges)
|  | Trips/day | Miles/trip | Total Trips | Number | Hours | Days | Number | Miles/trip | Hours/trip | Trips/tug
Off-Shore Disposal | Soil transported to temporary local staging areas along Ballona Creek (truck) | 670 | 1 | 7330 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Soil loaded on barge (crane) | 0 | 0 | 0 | 1 | 8 | 31 | 0 | 0 | 0 | 0
| Soil barged up to 55 miles to the US EPA Los Angeles ocean disposal site off San Pedro (LA-2, 30 miles) or the Newport Bay ocean disposal site off Newport Beach (LA 3, 55 miles) (30 barge trips) | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 110 | 12 | 31
Port of Los Angeles (barge) | Soil transported to temporary local staging areas along Ballona Creek (truck) | 670 | 1 | 7330 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Soil loaded on barge (crane) | 0 | 0 | 0 | 1 | 8 | 31 | 0 | 0 | 0 | 0
| Soil barged 30 miles from the shoreline of Port (30 barge trips) | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 30 | 8 | 31
Port of Los Angeles (truck) | Soil transported to temporary local staging areas along Ballona Creek (truck) | 670 | 1 | 7330 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Soil loaded on barge (crane) | 0 | 0 | 0 | 1 | 8 | 31 | 0 | 0 | 0 | 0
| Soil barged 33 miles from the shoreline of Port (30 barge trips) | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 30 | 8 | 31
| Soil trucked to facilities in Los Angeles County, Orange County, Riverside County, and Ventura County | 240 | 30.7-245 | 7330 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Landfill | Soil trucked to facilities in Los Angeles County, Orange County, Riverside County, and Ventura County | 240 | 30-79.3 | 7330 | 0 | 0 | 0 | 0 | 0 | 0 | 0
What is the anticipate horsepower for the tug boats? = 2,000 H.P.
Source: Appendix_3H.pdf

## Soil Export Alt2
After grading operations are complete, there may be up to 530,000 c.y. of excess soil that might be exported outside the project boundary for disposal. Export will occur during Sequence 24.
Option | Description | Haul Trucks |  |  | Crane |  |  | Tugs (to pull barges)
|  | Trips/day | Miles/trip | Total Trips | Number | Hours | Days | Number | Miles/trip | Hours/trip | Trips/tug
Off-Shore Disposal | Soil transported to temporary local staging areas along Ballona Creek (truck) | 670 | 1 | 35330 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Soil loaded on barge (crane) | 0 | 0 | 0 | 3 | 8 | 50 | 0 | 0 | 0 | 0
| Soil barged up to 55 miles to the US EPA Los Angeles ocean disposal site off San Pedro (LA-2, 30 miles) or the Newport Bay ocean disposal site off Newport Beach (LA 3, 55 miles) (150 barge trips) | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 110 | 12 | 50
Port of Los Angeles (barge) | Soil transported to temporary local staging areas along Ballona Creek (truck) | 670 | 1 | 35330 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Soil loaded on barge (crane) | 0 | 0 | 0 | 3 | 8 | 50 | 0 | 0 | 0 | 0
| Soil barged 30 miles from the shoreline of Port (150 barge trips) | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 30 | 8 | 50
Port of Los Angeles (truck) | Soil transported to temporary local staging areas along Ballona Creek (truck) | 670 | 1 | 35330 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Soil loaded on barge (crane) | 0 | 0 | 0 | 3 | 8 | 50 | 0 | 0 | 0 | 0
| Soil barged 33 miles from the shoreline of Port (150 barge trips) | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 30 | 8 | 50
| Soil trucked to facilities in Los Angeles County, Orange County, Riverside County, and Ventura County | 240 | 30.7-245 | 35330 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Landfill | Soil trucked to facilities in Los Angeles County, Orange County, Riverside County, and Ventura County | 240 | 30-79.3 | 35330 | 0 | 0 | 0 | 0 | 0 | 0 | 0
What is the anticipate horsepower for the tug boats? = 2,000 H.P.
Source: Appendix_3H.pdf

## Soil Export Alt3 (hidden)
After grading operations are complete, there may be up to 734,000,000 c.y. of excess soil that might be exported outside the project boundary for disposal. Export will occur during Sequence 24. | [8 empty] | NOTE: MATCHES ICF SPREADSHEET EXPORT VOLUME
Option | Description | Haul Trucks |  |  | Crane |  |  | Tugs (to pull barges)
|  | Trips/day | Miles/trip | Total Trips | Number | Hours | Days | Number | Miles/trip | Hours/trip | Trips/tug
Off-Shore Disposal | Soil transported to temporary local staging areas along Ballona Creek (truck) | 670 | 1 | 48930 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Soil loaded on barge (crane) | 0 | 0 | 0 | 3 | 8 | 67 | 0 | 0 | 0 | 0
| Soil barged up to 55 miles to the US EPA Los Angeles ocean disposal site off San Pedro (LA-2, 30 miles) or the Newport Bay ocean disposal site off Newport Beach (LA 3, 55 miles) (200 barge trips) | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 110 | 12 | 67
Port of Los Angeles (barge) | Soil transported to temporary local staging areas along Ballona Creek (truck) | 670 | 1 | 48930 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Soil loaded on barge (crane) | 0 | 0 | 0 | 3 | 8 | 67 | 0 | 0 | 0 | 0
| Soil barged 30 miles from the shoreline of Port (200 barge trips) | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 30 | 8 | 67
Port of Los Angeles (truck) | Soil transported to temporary local staging areas along Ballona Creek (truck) | 670 | 1 | 48930 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Soil loaded on barge (crane) | 0 | 0 | 0 | 3 | 8 | 67 | 0 | 0 | 0 | 0
| Soil barged 33 miles from the shoreline of Port (200 barge trips) | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 30 | 8 | 67
| Soil trucked to facilities in Los Angeles County, Orange County, Riverside County, and Ventura County | 240 | 30.7-245 | 48930 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Landfill | Soil trucked to facilities in Los Angeles County, Orange County, Riverside County, and Ventura County | 240 | 30-79.3 | 48930 | 0 | 0 | 0 | 0 | 0 | 0 | 0
What is the anticipate horsepower for the tug boats? = 2,000 H.P.
Source: Appendix_3H.pdf

## Soil Export Alt3a
After grading operations are complete, there may be up to 1,226,000 c.y. of excess soil that might be exported outside the project boundary for disposal. Export will occur during Sequence 24. | [8 empty] | NOTE: MATCHES FULL EXPORT
Option | Description | Haul Trucks |  |  | Crane |  |  | Tugs (to pull barges)
|  | Trips/day | Miles/trip | Total Trips | Number | Hours | Days | Number | Miles/trip | Hours/trip | Trips/tug
Off-Shore Disposal | Soil transported to temporary local staging areas along Ballona Creek (truck) | 670 | 1 | 81730 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Soil loaded on barge (crane) | 0 | 0 | 0 | 3 | 8 | 110 | 0 | 0 | 0 | 0
| Soil barged up to 55 miles to the US EPA Los Angeles ocean disposal site off San Pedro (LA-2, 30 miles) or the Newport Bay ocean disposal site off Newport Beach (LA 3, 55 miles) (330 barge trips) | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 110 | 12 | 110
Port of Los Angeles (barge) | Soil transported to temporary local staging areas along Ballona Creek (truck) | 670 | 1 | 81730 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Soil loaded on barge (crane) | 0 | 0 | 0 | 3 | 8 | 110 | 0 | 0 | 0 | 0
| Soil barged 30 miles from the shoreline of Port (330 barge trips) | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 30 | 8 | 110
Port of Los Angeles (truck) | Soil transported to temporary local staging areas along Ballona Creek (truck) | 670 | 1 | 81730 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Soil loaded on barge (crane) | 0 | 0 | 0 | 3 | 8 | 110 | 0 | 0 | 0 | 0
| Soil barged 33 miles from the shoreline of Port (330 barge trips) | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 30 | 8 | 110
| Soil trucked to facilities in Los Angeles County, Orange County, Riverside County, and Ventura County | 240 | 30.7-245 | 81730 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Landfill | Soil trucked to facilities in Los Angeles County, Orange County, Riverside County, and Ventura County | 240 | 30-79.3 | 81730 | 0 | 0 | 0 | 0 | 0 | 0 | 0
What is the anticipate horsepower for the tug boats? = 2,000 H.P.
Source: Appendix_3H.pdf

## Alt2
Sequence | Area | Title | Actions | Same as Alt 1? | Schedule Adjustment ? | Equipment Adjustment ?
PHASE 1
1 | B | Area "B" Southeast Gas Lines | 1a. Remove and relocate existing gas line | Y
2 | B | Area "B" South Enhancement | 2a. Create swale (10,000 CY wet cut) | Y
3 | A | Area "A' Gas Line Removal | 3a. Remove existing inactive gas line | Y
|  |  | 3b. Cut and cap gas line at Fiji Way | Y
25 | A & Property 1 | Gas Well Abandonment | 25a. Drill new well at SoCal Gas Plant to replace Del Ray 19 | Y
|  |  | 25b. Abandon and plug Del Ray 13, 14, 15, 17, 18, and 19 | Y
|  |  | 25c. Remove existing gas lines serving removed wells | Y
26 | A | Area A around Wells Clear & Grub | 26a. Remove vegetation around wells (2,000 CY) | Y
27 | A | Area A around Wells Grading and Export to West Area B | 27a. Excavate Area A and Export to West Area B (208,000 CY) | Y
28 | A | Finish Grading For Uplands | 28a. Finish grading around wells | Y
|  |  | 28b. Re-establish upland vegetation | Y
29 | B | Area B Abandon Wells | 29a. Drill new well at SoCal Gas Plant to replace Del Rey 9 and Vidor 18 | Y
|  |  | 29b. Abandon and plug Vidor 1, 2, 3, 5, 14, 18 and Del Rey 4, 5, 9, 11 | Y
|  |  | 29c. Remove existing pipelines | Y
30 | B | Area B around Wells Clear & Grub | 30a. Remove vegetation around wells (2,000 CY) | Y
31 | B | Finish Grading For Uplands | 31a. Finish grading around wells | Y
|  |  | 31b. Re-establish upland vegetation | Y
4 | A & B | Pedestrian/Bike Bridge | 4a. Construct temporary & portion of final re-routed trail to existing trail | Y
|  |  | 4b. Construct new pedestrian/bike bridge over Ballona Creek | Y
|  |  | 4c. Reroute Ballona Creek Bike Trail under Culver Blvd Bridge | Y
5 | A & C | Lincoln Bridge | 5a. Build Lincoln Bridge next to Culver Bridge to connect Area A to Area C North | Y
6 | A | Clear, Grub, and Stockpile Area "A" | 6a. Remove vegetation from Area A (54,400 CY dry cut) | Y
|  |  | 6b. Remove trash | Y
|  |  | 6c. Stockpile | Y
7 | A | Excavate Area "A" | 7a. Remove 36" concrete pipe near center of Area A | Y
|  |  | 7b. Excavate old fill from Area A (1,384,000 CY wet cut, see note) | Y
|  |  | 7c. Dig below (over excavate) future levees (30,000 CY dry cut) | Y
8 | A | Area "A' Construct North Levee | 8a. Grade and construct new levee around Area A (125,300 CY fill) | Y
|  |  | 8b. Protect Del Ray 13, 14, 15, 17, and 19 | N
9 | B & Property 1 | Area "B" North Gas Line Relocation & Well Abandonment | 9a. Drill new well at SoCal Gas Plant to replace Del Ray 12 | Y
|  |  | 9b. Abandon and plug Del Rey 12 | Y
|  |  | 9c. Remove/relocate existing pipelines | Y
10 | B | Area "B" North Clear & Grub | 10a. Remove vegetation from Area B North and Area B West (25,000 CY wet cut) | Y
|  |  | 10b. Remove trash | Y
11 | B | Area "B" North Over-Excavate and Stockpile | 11a. Excavate Area B North (56,700 CY wet cut) | Y
|  |  | 11b. Dig below (over excavate) future levees (11,700 3,000 CY wet cut) | N
12 | B | Construct Area "B" Levee | 12a. Construct Area B levees (95,600 266,200 CY) | Y
13 | B | Clear, Grub, and Stockpile Area "B" East | 13a. Remove vegetation in Area B East stockpile area (4,600 CY wet cut) | Y
|  |  | 13b. Stockpile and prepare for fill | Y
14 | B | Area "B" East Stockpile Grading | 14a. Grade Area B east and import from Area A (80,000 324,000 CY import from Area A) | N | Increase from 20 to 85 days
15 | C | Clear & Grub Area "C" North & South | 15a. Protect Demo baseball fields and structures. | N | Add 15 Days
|  |  | 15b. Clear vegetation from Area C North (56,000 CY dry cut) & South (15,000 51,000 CY dry cut) | N | Increase from 15 to 25 days
|  |  | 15c. Re-align and replace Marina ditch (45,000 CY wet cut) | Y
16 | A & C | Area "A" Grading and Export to Area "C" North & South | 16a. Excavate Area A and export to C South (300,000 540,000 CY total) | N | Increase from 75 to 135 days
|  |  | 16b. Excavate Area A and export to C North (720,000 500,000 CY ultimate total; 403,000 183,000 CY at this sequence until levee is breached) | N | Decrease from 110 to 50 days
17 | C | Finish Grading for Uplands Area "C" South | 17a. Finish grading Reconstruct ballfields and structures and detailed grading in Area C South | N | Increase from 15 to 65 days | Use 7
|  |  | 17b. Re-establish upland vegetation | Y
18 | B | Area "B" New and Reconstructed Culverts | 18a. Install culverts under Culver/Jefferson Blvd, Gas Co Rd., and FWM berm; modify existing culvert under west end of Culver Blvd. | Y
|  |  | 18b. Remove existing FWM pipes and outlets | Y
|  |  | 18c. Construct new FWM outlet and spillway | Y
19 | A & B | Area "A" and Area "B" North Excavate and Breach Existing Levees | 19a. Excavate Ballona Creek Channel in Areas A and B North (277,800 CY cut) | Y
20 | A & B | Area "A" and Area "B" North Block and Fill Existing Levees | 20a. Install temporary pipe | Y
|  |  | 20b. Temporary block then fill existing Ballona Creek (269,100 CY fill from Seq 19) | Y
21 | A & B | Area "A" and Area "B" North Remove Existing Levees | 21a. Remove old Ballona Creek levee (424,400CY) and excavate new channel meanders - Export to Area C North, quantities included in Sequence 16, ultimate. | Y
22 | B | Area "B" West Fire Access Road | 22a. Construct maintenance and fire road in Area B West | Y
|  |  | 22b. Reconstruct Area B parking lot | Y
23 | A & B | Bike Path, Pedestrian Walkway and Amenities | 23a. Construct bike and ped trails on levees | Y
|  |  | 23b. Construct County Parking Structure Foundation | Y
|  |  | 23c. Construct County Parking Structure | Y
24 | A | Export | 24a. Export final excess dirt quantity (Assume 530,000 CY) | N | Increase from 35 to 150 days
PHASE 2
Area A Gas Well Removal and Restoration
25 | A & Property 1 | Gas Well Abandonment | 25a. Drill new well at SoCal Gas Plant to replace Del Ray 19 | Y
|  |  | 25b. Abandon and plug Del Ray 13, 14, 15, 17, 18, and 19 | Y
|  |  | 25c. Remove existing gas lines serving removed wells | Y
26 | A | Area A around Wells Clear & Grub | 26a. Remove vegetation around wells (2,000 CY) | Y
27 | A | Area A around Wells Grading and Export to West Area B | 27a. Excavate Area A and Export to West Area B (208,000 CY) | Y
28 | A | Finish Grading For Uplands | 28a. Finish grading around wells | Y
|  |  | 28b. Re-establish upland vegetation | Y
Area B wells
29 | B | Area B Abandon Wells | 29a. Drill new well at SoCal Gas Plant to replace Del Rey 9 and Vidor 18 | Moved Up in Sequence
29b. Abandon and plug Vidor 1, 2, 3, 5, 14, 18 and Del Rey 4, 5, 9, 11
29c. Remove existing pipelines
30 | B | Area B around Wells Clear & Grub | 30a. Remove vegetation around wells (2,000 CY)
31 | B | Finish Grading For Uplands | 31a. Finish grading around wells
31b. Re-establish upland vegetation
Area B West
32 | B | Area "B" West Clear & Grub | 32a. Remove vegetation in Area B West (76,000 CY)
33 | B | Area "B" West Grading and Levee Extention | 33a. Install temporary flexible storm drain
33b. Dig below (over excavate) levees (10,800k CY wet cut)
33c. Grade Area B West channels, construct salt pan berm, and construct levee with import from stockpile from Area B North and East at 248,000 CY (31,200 + 216,800 CY (291,800 less 49,000 and 26,000))
34 | B | Area "B" West Excavate and Breach Existing Levees | 34a. Breach existing levee in Area B West and place in Stability berms (75,000 CY wet = 26,000 + 49,000)
35 | B | Finish Bike Path, Pedestrian Walkway and Amenities | 35a. Construct maintenance and fire access road and bike path on new levee.
36 | B | Finish Grading For Uplands | 36a. Finish grading Area B East
36b. Re-establish upland vegetation
SEPARATE PHASE
29 | B | Area B Abandon Wells | 29b. Abandon and plug Vidor 1, 2 and Del Ray 4, 5, 9 | Y
|  |  | 29c. Remove existing pipelines | Y
30 | B | Area B around Wells Clear & Grub | 30a. Remove vegetation around wells (2,000 CY) | Y
31 | B | Finish Grading For Uplands | 31a. Finish grading around wells | Y
|  |  | 31b. Re-establish upland vegetation | Y
Note on D40: Nick Garrity: 173,00 + 92,500
Note on D57: Nick Garrity: Please provide backup for this quantity

## Alt3
Sequence | Area | Title | Actions | Same as Alt 1? | Schedule Adjustment ? | Schedule Adjustment ?
1 | B | Area "B" Southeast Gas Lines | 1a. Remove and relocate existing gas line | Y
2 | B | Area "B" South Enhancement | 2a. Create stormwater detention/treatment swale/wetland (10,000 CY wet cut) | Y
3 | A | Area "A' Gas Line Removal | 3a. Remove existing inactive gas line | Y
|  |  | 3b. Cut and cap gas line at Fiji Way | Y
25 | A & Property 1 | Gas Well Abandonment | 32a. Drill new well at SoCal Gas Plant to replace Del Rey 17 and 19 | Y
|  |  | 32b. Abandon and plug Del Rey 13, 14, 15, 17, 18 and 19 | Y
|  |  | 32c. Remove existing gas lines serving removed wells | Y
|  |  | 31a. Finish grading around wells | N
9 | B & Property 1 | Area "B" North Gas Line Relocation & Well Abandonment | 31b. Re-establish upland vegetation | N
|  |  | 9c. Remove existing pipelines | Y
29 | B | Area B Abandon Wells | 29b. Abandon and plug Vidor 1, 2, 3, 5, 14, 18 and Del Rey 4, 5, 9, 11 | Y
|  |  | 29b. Remove existing pipelines | Y
30 | B | Area B around Wells Clear & Grub | 30a. Remove vegetation around wells (2,000 CY) | Y
31 | B | Finish Grading and Habitat Establishment | 31a. Finish grading around wells | Y
|  |  | 31b. Establish vegetation | Y
4 | A & B | Pedestrian/Bike Bridge | 4a. Construct temporary & portion of final re-routed trail to existing trail | Y
|  |  | 4b. Construct new pedestrian/bike bridge over Ballona Creek | Y
|  |  | 4c. Reroute Ballona Creek Bike Trail under Culver Blvd Bridge | Y
5 | A & C | Lincoln Bridge | 5a. Build Lincoln Bridge next to Culver Bridge to connect Area A to Area C North | Y
6 | A | Clear, Grub, and Stockpile Area "A" | 6a. Remove vegetation from Area A (54,400 CY dry cut) | Y
|  |  | 6b. Remove trash | Y
|  |  | 6c. Stockpile | Y
7 | A | Excavate Area "A" | 7a. Remove 36" concrete pipe near center of Area A | Y
|  |  | 7b. Excavate old fill from Area A (1,384,000 999,700CY wet cut, see note) | Y | Decrease from 555 to 400 days
|  |  | 7c. Dig below (over excavate) future levees (30,000 CY dry cut) | Y
8 | A | Area "A' Construct North Levee | 8a. Grade and construct new levee around Area A (125,300 CY fill) | Y
|  |  | 8b. Protect Del Ray 13, 14, 15, 17, and 19 | Y
10 | B | Area "B" North Clear & Grub | 10a. Remove vegetation from Area B North and Area B West (168,000 CY wet cut) | Y
|  |  | 10b. Remove trash | Y
11 | B | Area "B" North Over-Excavate and Stockpile | 11a. Excavate Area B North and perimeter of Area B West (61,000 CY wet cut) | Y
|  |  | 11b. Dig below (over excavate) future levees (27,000k CY wet cut) | Y
12 | B | Construct Area "B" Levee | 12a. Construct Area B levees (739,000CY fill - reuse of soils from Area B = 52k and import from Area A = 859k cut resulting in 687k fill) | Y
13 | B | Clear, Grub, and Stockpile Remove Invasives for Area "B" East | 13a. Remove vegetation Invasives in Area B East (18,000 CY wet cut) | N
|  |  | 13b. Stockpile and prepare for fill | N
14 | B | Area "B" East Stockpile Grading | 14a. Grade Area B east and import from Area A (80,000 340,000 CY import from Area A) | N
15 | C | Clear & Grub Area "C" North & South | 15a. Protect baseball fields and structures. | N
|  |  | 15b. Clear vegetation from Area C North (56,000 CY dry cut) & South (15,000CY dry cut) | N
|  |  | 15c. Re-align and replace Marina ditch (45,000 CY wet cut) | Y
19 | A | Area "A" Excavate New Channel | 19a. Excavate Ballona Creek Channel in Area A (277,800 190,900 CY cut) | N | Decrease from 130 to 55 days
16 | A & C | Area "A" Grading and Export to Area "C" North & South Off-Site | 16a. Excavate Area A and export to C South (300,000 CY total) Off-Site (1,230,000 CY Total; Split into Seq 's 16 (859k), 19/20 (195k), 21 (166k), and 24 (10k)) | N | Increase from 75 to 340 days
|  |  | 16b. Excavate Area A and export to C North (720,000 CY ultimate total; 403,000 CY at this sequence until levee is breached) | N | Deleted
17 | C | Finish Grading Remove invasives for Uplands Area "C" North & South | 17a. Finish grading Remove invasives Area C North & South | N | Increase from 15 to 45 days | Use 14
|  |  | 17b. Re-establish upland vegetation | Y
18 | B | Area "B" New and Reconstructed Culverts | 18a. Install culverts under Culver and Jefferson Blvd | Y
|  |  | 18b. Remove existing FWM pipes and outlets | Y
|  |  | 18c. Construct new FWM outlet and spillway | Y
20 | A & B | Area "A" and Area "B" North Block and Fill Existing Levees | 20a. Install temporary pipe | Y
|  |  | 20b. Temporary block then fill existing Ballona Creek (235,000 CY fill from Seq 19) | Y
21 | A & B | Area "A" and Area "B" North Remove Existing Levees | 21a. Remove old Ballona Creek levee (Assume 45,000 CY wet cut; 121,000CY dry cut) - Export to Area C North, quantities included in Sequence 16, ultimate. Off-Site | N
22 | B | Area "B" West Fire Access Road | 22a. Construct maintenance and fire road in Area B West | Y
|  |  | 22b. Reconstruct Area B parking lot | Y
23 | A & B | Bike Path, Pedestrian Walkway and Amenities | 23a. Construct bike and ped trails on levees | Y
|  |  | 23b. Construct County Parking Structure Foundation | Y
|  |  | 23c. Construct County Parking Structure | Y
xx | A | Area "A" Excavate New Channel | Install culverts in existing north Ballona Creek levee | N | ADDED LINE, 20 days | Use 1
24 | A | Export | 24a. Export final excess dirt quantity (Assume 1,230,000 CY, per line 16a.) | N | See 16a
26 | A | Area A around Wells Clear & Grub | 26a. Remove vegetation around wells (2,000 CY) | N
27 | A | Area A around Wells Grading and Export to West Area B | 27a. Excavate Area A and Export to West Area B (208,000 CY) | N
28 | A | Finish Grading For Uplands | 28a. Finish grading around wells | N
|  |  | 28b. Re-establish upland vegetation | N
|  | SEPARATE PHASE | 31a. Finish grading around wells | N
9 | B & Property 1 | Area "B" North Gas Line Relocation & Well Abandonment | 31b. Re-establish upland vegetation | N
|  |  | 9c. Remove existing pipelines | Y
29 | B | Area B Abandon Wells | 29b. Abandon and plug Vidor 1, 2, 3, 5, 14, 18 and Del Rey 4, 5, 9, 11 | Y
|  |  | 29b. Remove existing pipelines | Y
30 | B | Area B around Wells Clear & Grub | 30a. Remove vegetation around wells (2,000 CY) | Y
31 | B | Finish Grading and Habitat Establishment | 31a. Finish grading around wells | Y
|  |  | 31b. Establish vegetation | Y
Area B West
32 | B | Area "B" West Clear & Grub | 32a. Remove vegetation in Area B West (76,000 CY) | N
33 | B | Area "B" West Grading and Levee Extention | 33a. Install temporary flexible storm drain | N
|  |  | 33b. Dig below (over excavate) levees (10,800k CY wet cut) | N
|  |  | 33c. Grade Area B West channels, construct salt pan berm, and construct levee with import from stockpile from Area B North and East at 248,000 CY (31,200 + 216,800 CY (291,800 less 49,000 and 26,000)) | N
34 | B | Area "B" West Excavate and Breach Existing Levees | 34a. Breach existing levee in Area B West and place in Stability berms (75,000 CY wet = 26,000 + 49,000) | N
35 | B | Finish Bike Path, Pedestrian Walkway and Amenities | 35a. Construct maintenance and fire access road and bike path on new levee. | N
36 | B | Finish Grading For Uplands | 36a. Finish grading Area B East | N
|  |  | 36b. Re-establish upland vegetation | N

## Alt 4
Sequence | Area | Title | Actions | Same as Alt 1?
NEW | A, B, C | Restoration | Invasive species removal and volunteer-based restoration | N (ICF will assume no heavy-equipment or trucks. Emissions will be generated by volunteer trips to the site).
1 | C | Clear and Grub Area "C" South | 1a. Remove vegetation from Area C South | N
|  |  | 1b. Demolish baseball fields | N
|  |  | 1c. Demolish structures | N
|  |  | 1d. Remove trash | N
2 | C | Area "C" South Grading | 2a. Grade Area C South | N
|  |  | 2b. Construct Ecology Center and new ball fields | N
3 | B | Area "B" Southeast Gas Lines | 3a. Remove and relocated existing gas line | N
4 | B | Area "B" Temporary Storm Drain | 4a. Install temporary flexible storm drain pipe | N
5 | B | Area "B" South Enhancement | 5a. Create swale | N
6A | A and Property 1 | Area "A' Gas Line Removal | 6Aa. Remove existing inactive gas line | N
|  |  | 6Ab. Cut and cap gas line at Fiji Way | N
6B | A and Property 1 | Area "A" Gas Line Removal & Well Abandonment | 6Ba. Remove existing inactive gas line | N
|  |  | 6Bb. Cut and cap gas line at Fiji Way | N
|  |  | 6Bc. Drill new well at SoCal Gas Plant to replace Del Ray 17 | N
|  |  | 6Bd. Drill new well at SoCal Gas Plant to replace Del Ray 19 | N
|  |  | 6Be. Abandon and plug Del Ray 13, 14, 15, 17, and 19 | N
|  |  | 6Bf. Remove existing gas lines serving removed wells | N
7 | A & B | Pedestrian/Bike Bridge | 7a. Connect re-routed trail to existing trail | N
|  |  | 7b. Construct new pedestrian/bike bridge over Ballona Creek | N
|  |  | 7c. Reroute Ballona Creek Bike Trail under Culver Blvd Bridge | N
8 | A & C | Lincoln Bridge | 8a. Build Lincoln Bridge next to Culver Bridge to connect Area A to Area C North | N
9 | A | Clear and Grub Area "A" | 9a. Remove vegetation from Area A | N
|  |  | 9b. Remove trash | N
|  |  | 9c. Stockpile | N
10 | A | Excavate Area "A" | 10a. Remove 36" concrete pipe near center of Area A | N
|  |  | 10b. Excavate old fill from Area A | N
|  |  | 10c. Dig below (over excavate) future levees | N
11A | A and Property 1 | Area "A' Construct North Levee | 11Aa. Grade and construct new levee around Area A | N
|  |  | 11Ab. Protect Del Ray 13, 14, 15, 17, and 19 | N
11B | A and Property 1 | Area "A' Construct North Levee | 11Ba. Grade and construct new levee around Area A | N
12A | B and Property 1 | Area "B" North Gas Line Relocation & Well Abandonment | 12Aa. Drill new well at SoCal Gas Plant to replace Del Ray 12 | N
|  |  | 12Ab. Abandon and plug Del Ray 12, Vindor 3 | N
|  |  | 12Ac. Remove existing pipelines | N
12B | B and Property 1 | Area "B" North Gas Line Relocation & Well Abandonment | 12Ba. Drill new well at SoCal Gas Plant to replace Del Ray 12 | N
|  |  | 12Bb. Abandon and plug Vindor 1, 2, 3 and Del Ray 4, 5, 9, 12 | N
|  |  | 12Bc. Remove existing pipelines | N
13 | B | Area "B" North Clear & Grub | 13a. Remove vegetation from Area B North and Area B West | N
|  |  | 13b. Remove trash | N
14 | B | Area "B" North Over-Excavate and Stockpile | 14a. Excavate Area B North and perimeter of Area B West | N
|  |  | 14b. Dig below (over excavate) future levees | N
15 | B | Construct Area "B" Levee | 15a. Construct Area B levees | N
16 | B | Clear and Grub Area "B" East | 16a. Remove vegetation in Area B East | N
|  |  | 16b. Stockpile and prepare for fill | N
17 | B | Area "B" East Grading | 17a. Grade Area B east and prepare for fill | N
18 | C | Clear & Grub Area "C" North | 18a. Clear vegetation from Area C North | N
|  |  | 18b. Re-align and improve Marina ditch | N
19 | A & C | Area "A" Grading and Export to Area "C" North | 19a. Excavate Area A | N
|  |  | 19b. Export fill to Area C North and offsite | N
20 | C | Finish Grading for Uplands Area "C" North | 20a. Finish grading Area C North | N
|  |  | 20b. Re-establish upland vegetation | N
21 | A & B | Bike Path, Pedestrian Walkway and Amenities | 21a. Construct bike and ped trails on levees | N
22 | B | Area "B" Box Culverts | 22a. Install box culverts under Culver and Jefferson Blvd | N
|  |  | 22b. Remove existing pipes and outlets | N
|  |  | 22c. Construct new outlet | N
23 | A & B | Area "A" and Area "B" North Excavate and Breach Existing Levees | 23a. Excavate Ballona Creek Channel in Areas A and B North | N
24 | A & B | Area "A" and Area "B" North Block and Fill Existing Levees | 24a. Install temporary pipe | N
|  |  | 24b. Temporary block then fill existing Ballona Creek | N
25 | A & B | Area "A" and Area "B" North Remove Existing Levees | 25a. Remove old Ballona Creek levee | N
22 | B | Area "B" West Fire Access Road | 22a. Construct maintenance and fire road in Area B West | N
|  |  | 22b. Reconstruct Area B parking lot | Y
27 | B | Area "B" West Grading | 27a. Remove vegetation in Area B West | Y
|  |  | 27b. Grade Area B West | Y
28 | B | Extension of Bike Path along South Levee to Playa Del Rey | 28a. Construct bike and ped trails on levee in Areas B West and North | Y
29 | B | Area "B" West Excavate and Breach Existing Levees | 29a. Breech existing levee in Area B West | Y
30 | B | Area "B" West Remove Existing Levees | 30a. Remove existing levee in Area B West | Y
|  |  | 30b. Remove interim levee between Area B West and Area B North | Y
31 | B | Export from Area "B" West to Area "B" East | 31a. Move extra soil from Area B West to Area B East | Y
32 | B | Finish Grading For Uplands | 32a. Finish grading Area B East | Y
|  |  | 32b. Re-establish upland vegetation | Y

## Well Construction (hidden)
Well Site Preparation (SP)
Two inches of compacted ¾-inch base rock will be used to bring the access roads to the wells to 12 feet in width on the straightaways and 20 feet in width at the corner of the turns
Two inches of compacted ¾-inch base rock will be used to create a work pad 120 feet x 170 feet centered at the wellhead
| Days | 5 | per well
Well Abandonment (WA)
| Days | 45 | per well (max) [min is 33]
| Hours | 12 | per day
| Equipment | 1 | Mobile Production Rig
|  | 1 | Mobile Rig Pump
|  | 1 | Rig Equipment Truck
|  | 1 | Portable Generator
|  | 1 | Service Truck
|  | 1 | Cement Pump Truck
|  | 1 | Bulk Cement Truck
|  | 3 | Wireline Logging Trucks
|  | 1 | 120 bbl or 80 bbl Vacuum Truck
|  | 6 | Service Pickup Trucks
|  | 1 | Delivery Truck (Tractor/Flatbed Trailer)
|  | 1 | Stinger Truck with flatbed trailer
Drilling New Well (DNW)
| Days | 50 | per well (max) [min is 35]
| Hours | 24 | per day
| Equipment | 1 | Drilling Rig
|  | 2 | Skid Mounted Rig Pumps
|  | 1 | 600 bbl Mud Pit with shakers
|  | 2 | Diesel (or NatGas powered) Electric Generators
|  | 1 | Accumulator Unit
|  | 1 | Top Drive Power Unit
|  | 2 | Portable Generators
|  | 1 | Cement Pump Truck
|  | 1 | Bulk Cement Truck
|  | 3 | Wireline Logging Trucks
|  | 2 | 120 bbl or 80 bbl Vacuum Truck
|  | 1 | Service Truck
|  | 8 | Service Pickup Trucks
|  | 2 | Delivery Truck (Tractor/Flatbed Trailer)
|  | 1 | Stinger Truck with flatbed trailer
|  | 1 | Forklift
|  | 1 | Rig Equipment Truck
|  | 2 | 90 or 150 ton Cranes
|  | 30-50 | Flat Bed Trailers and Trucks
|  | 1 | Backhoe
New Well Completion Operations (NWCO)
| Days | 10 | per well (max) [min is 7]
| Hours | 12 | per day
| Equipment | 1 | Mobile Production Rig
|  | 1 | Mobile Rig Pump
|  | 1 | Rig Equipment Truck
|  | 1 | Portable Generator
|  | 1 | Service Truck
|  | 2 | Wireline Trucks
|  | 1 | 120 bbl or 80 bbl Vacuum Truck
|  | 5 | Service Pickup Trucks
|  | 1 | Delivery Truck (Tractor/Flatbed Trailer)
|  | 1 | Stinger Truck with flatbed trailer
Investigate and Remediate Abandoned Wells (IRAW)
| Days | 60 | per well (2 months)
| Hours |  | per day
| Equipment | 1 | Drilling Rig
|  | 1 | Backhoe
|  | 4 | Truck
Pipeline Relocation
| Days | 30
| Hours |  | per day
| Equipment | 2 | Side boom tractors
|  | 1 | Large 60 ton crane
|  | 2 | Rubber tire backhoe
|  | 2 | Excavators
|  | 2 | Boom truck crane
|  | 4 | Welding trucks
|  | 4 | Pickup trucks
|  | 2 | Gasoline powered air compressors operating < than 50 HP
|  | 1 | Gasoline powered hydrostatic pump
|  | 2 | Gasoline powered light plants
|  | 4 | Gasoline powered traffic control arrow boards
Source: Appendix_3K.pdf

## Alt 1 Notes (hidden)
Project Feature | Relevant PD Detail
Realigned Ballona Creek Channel | 250 feet wide and 2-8 feet deep
New levees
New water control features (tide gates and culverts)
Improved habitat
Urban Ecology Center (Area C South) | 46,000 square feet (33,000 square feet footprint); 50 staff per day; Platinum certification (green roof, zero net energy with solar PV, solar thermal, biogas fuel cell, efficient HVAC, lighting, building envelope, passive heating/cooling, high-efficiency and low-flow fixtures, gray water treatment system, rainwater harvesting.
Reconfigured ball fields (Area C South) | Four fields (one 90-foot and three 60-foot) turf; reconstruction of existing concession stand
Parking | Existing dirt (100'X150') lot will be replaced with three smaller parking areas. Another lot (covered with solar PV) would be provided at the Ecology Center. Porous pavement would be used.
Trails | 4,800 feet of decomposed granite, gravel, concrete, or asphalt
Bike Access | 100 foot detour loop of concrete or asphalt
Native landscape | Riparian woodland created
Site Parking | Area C South parking at Ecology Center; Construction of new three-level garage on existing DBH lot in Area A; Paving of existing dirt lot in Area B West.
Pedestrian and Bicycle Network
Pedestrian and Bike Trails | 19,000 feet of trail in Areas A and B (bike path is paved; ped path is granite)
Pedestrian Only Trails | 10,000 feet of trail (granite)
Pedestrian Boardwalk | 2,000 feet
Bridges | New bridge over Ballona Creek (25 feet wide); New bridge over Lincoln Boulevard
Relocated gas wells | Abandoned or relocated to "Property 1"
Movement of excess fill
Area A | 139 acres | Undeveloped, four SoCal gas mointoring wells, two paved parking lots (240 stall BH and 60 stall local sheriff)
Area B | 338 acres | Remnant unfilled wetlands with abandoned agricultural lands; SoCal gas well; unpaved (100x150' parking lot)
Area C | 66 acres | Undeveloped with the exception of the ball fields and minor supporting structures
Property 1 | 8141 Gulana Avenue | 13 active SoCal gas wells and four abondoned wells
Property 2 | Existing parking lot | Boat storage and parking

## Alt 1 Features (hidden)
Walking | 4800 | LF | C South | Decomposed granite, boardwalk, permeable concrete or asphalt
Bike Loop | 100 | LF | C South | Permeable concrete or asphalt
Walking + Biking | 1900 | LF | Area A + B | Bike paved with permeable concrete or asphalt; walking side decomposed granite
Trails | 10000 | LF | - | Decomposed granite
Boardwalks | 2000 | LF | - | Wood
Bridges | 2 | bridges | Area C North + A | -
Parking Lot | 292 | spaces | C South | Porous pavement (replaces existing gravel lot near ball fields)
Parking Lot | 43 | spaces | Area B West | Porous pavement (replaces existing gravel lot)
Parking Structure | 302 | spaces | Area A | Concrete
Source: Project Description