## Revised 2013 MAST Report Timeline (revised 11/15/2013, subject to change)

The timeline for completing the 2013 MAST report was revised again due to the Federal Government Shut-Down. We can no longer maintain the previously envisioned end-December completion date and now aim for completion in early February, before the annual IEP workshop. This timeline includes a special Stakeholder Group meeting (date TBD) to provide stakeholders with an opportunity to provide chapter 6 input using a “bulleted list” of key points from chapter 6 as the basis for discussion. The IEP Coordinators developed and agreed to this approach on Nov. 7.

New dates & activities in **red.**

**July 22: Draft MAST report (v4) posted on the IEP website for a 40-day public review period**

August 14: Draft MAST report presentation and discussion with IEP Stakeholder Group (see <http://www.water.ca.gov/iep/activities/calendar.cfm> for meeting details)

COB August 30: Public draft MAST report review period closes

Sept 5: MAST report review update at Coordinators meeting

Sept 11: Public review comments organized, compiled and sent to MAST. Brief public review summary prepared for IEP Coordinators, Directors, and Stakeholders (Anke Mueller-Solger, DSC)

Sept 11: Special Meeting of the IEP Stakeholder Group to allow for “Focused Discussion on MAST”

Sept 12: MAST meeting to consider and discuss reviewer comments and MAST report revisions

Sept 13: Proposed revisions to MAST timeline and chapter authorship to MAST

Sept 19: Independent peer review comments received from DSP

Sept 17: MAST report progress & review update to IEP Directors

Sept 24: All additional review comments organized, compiled and sent to MAST Brief summary of all reviews prepared for IEP Coordinators, Directors, and Stakeholders (Kris Jones, DWR, and Anke Mueller-Solger, DSC)

**October 1-16: FEDERAL GOVERNMENT SHUT-DOWN – 8 MAST AUTHORS FURLOUGHED**

October 10: Half-MAST meeting (State only) – discuss revision progress and need to reschedule off-site meeting and revise timeline due to shut-down

October 16: CANCELLED DUE TO FEDERAL GOVERNMENT SHUT-DOWN: Intensive 1-day local MAST off-site to work through MAST report revisions and discuss completion of chapter 6

October 30: MAST report presentation (poster) at 2013 State of the Estuary Conference

COB Nov 13: MAST report section authors revise sections in consideration of reviewer comments pertaining to their sections and add chapter 6 content

Nov 14: Rescheduled intensive 1-day local MAST off-site at UCD to work through MAST report revisions, talk about how to incorporate recent relevant publications, and discuss completion of chapter 6

Nov 19: Larry compiles edits to date, sends to MAST

Nov 20: Monthly MAST meeting to discuss additional report issues and the future of MAST

Nov 26: MAST authors check Larry’s Compilation; Chpt 6 authors send initial draft bullets to MAST

**November 29:** MAST authors complete revisions to chapters 1-5 of draft MAST report, develop initial sections of Chapter 6, and compile initial (v A) **bulleted list of “key points” contained in the evolving draft Chapter 6** **for special meeting with Stakeholder Group and for briefing IEP Directors.**

**COB December 4:** Revised draft MAST report (v5) with initial sections of first draft chapter 6 and appendices (review summary, draft chapter 6 bullets, perhaps supplemental figures) compiled and sent to MAST and Coordinators for further review and revisions.

**December 5, am:** Draft MAST report presentation and discussion with IEP Coordinators.

Intended outcome: **Coordinators provide feedback on chapter 6 bullets list (v A).**

**COB Dec. 6:** Chapter 6 bullets list revised (v B) by chapter 6 authors and sent to MAST & Coordinators for additional feedback

***Dec. 9-13 (TBD):*** IEP Stakeholder Group in-person & webex meeting: MAST report revision overview (Anke), in-depth discussion of Chapter 6 bullets list (v B).

**COB Dec. 9:**MAST authors complete revisions to draft MAST report (v5), including first full version of Chapter 6

**Dec 12:** Monthly MAST meeting to discuss outstanding report revision issues, “lessons learned” during this phase of MAST, and future of MAST.

**COB Dec. 13:**Revised draft MAST report (v6) compiled and sent to MAST and Coordinators

**Dec 16, am:** Meeting notes from Stakeholder Group meeting (Dave VR) provided to MAST for further development of Chapter 6 content and revision of Chapter 6 bullets list.

December 17: MAST report progress focusing on chapter 6 “key points” bullets and future of MAST discussion with IEP Directors.

**COB Dec. 20:** Coordinators provide review comments on draft MAST report (v6) **with special attention given to chapter 6**

**COB Dec. 31:** MAST authors complete final revisions to draft MAST report, including Chapter 6.

January 2: Draft MAST report discussion with IEP Coordinators. Intended outcome: Coordinators provide final report guidance.

**COB January 8:** Final draft MAST report (v7) compiled and sent to MAST.

January 9: Monthly MAST meeting to discuss outstanding report revision issues, “lessons learned” during this phase of MAST, and future of MAST.

**COB Jan. 23:** **Proposed FINAL MAST REPORT (v8)** completed and sent to Coordinators for approval.

***Jan. or Feb.: MAST presentation(s) at rescheduled DSP/SWRCB flows workshop???***

February 6: Final draft MAST report presentation and discussion with IEP Coordinators; discussion of future direction of MAST. Intended outcome: Coordinators approve release of **Proposed FINAL MAST REPORT (v8)** and it is posted on the IEP website.

February 13: Monthly MAST meeting to prepare and discuss MAST presentation(s) at annual IEP workshop.

**February TBD:** Final draft MAST report presentation and discussion with IEP

Directors; discussion of future MAST direction. Intended outcome: Directors give guidance for next phase of MAST.

Feb. 26-28: MAST presentation(s) at annual IEP workshop.