## Sheet1
OSPR SCIENTIFIC ACP Workgroup - 2014 Work Plan
ITEM | TASK | ASSIGNMENT |  |  |  | ACTIVITIES COMPLETED (2013) | ACTIVITIES PLANNED (2014) | PRIORITY STATUS
A. | Area Contingency Plan (ACP) Workgroup
1 | Refine ACP Workgroup 2014 Work Plan. | Jennings |  |  | The FWC reviewed its work plan at the Dec meeting. | Refined ACP Workgroup Work Plan | Refine ACP Work Plan | A Ongoing
2 | Coordinate with other Scientific Workgroups on overlapping matters | Jennings | Shannah Anderson (District I) resigned from the position in August. Linda Hayes Sanders was appointed to the Alternate to At-Large position, replacing Scott Etzel. | Gordon Becker became the District I representative. Three seats were expired in February. Applications were accepted from public. Interviews were taken place on Nov 20th and Dec 18th. Tiffany Tokiwa resigned from her District position in December. | Greg Feere became the District 5 representative. Frank Pereira, At-Large seat, passed away on April 14, 2003. Linda Sanders took the At-Large seat. Alternate-to-At-Large seat became vacant. Candidates for the Alternate seat were reviewed. | Developed Workgroup Minutes | Develop Workgroup Minutes | A Ongoing
i | Cultural and Historic Workgroup | Dayton |  |  |  | Discussed ACP sections of overlap | Review appropriate sections of ACP and incorporate new language from Lori Chumney | A Ongoing
ii | SCAT Workgroup | Haffner |  |  |  | Discussed ACP sections of overlap | Discuss ACP sections of overlap | B Ongoing
iii | SISRS Workgroup | Schommer |  | FWC obtained a list of addresses and phone numbers of the Fish and Wildlife Committees located in California. FWC considers contacting a few Committees. |  | Updated SISRS not available for ACP Revision | Work with old SISRs and develop mechanism for making documents ADA Compliant for 2014. | B Ongoing
B. | ACP Statewide Consistency
1 | Volume I (Sections 1000 to 9000) Review and Consistency | Jennings |  |  |  | Reviewed Volume I for all Sectors | Address consistency issues for 2014 revision | B Ongoing
i | Sector San Francisco | Jennings | The Committee revised the guidelines on the RFP in 2001 in order to clarify specific funding requirements. Contra Costa Times published a small article that contained the grant funding information. In total, six grant applications were submitted between January and December of 2001. | RFPs were sent to all Watershed Forum mailing list people, in additions to FWC mailing list. | Ten projects were funded in April. One project was funded in September. Ten reports were submitted. Some projects were not finished completely by the end of this year, but the Committee allowed their project extension so long as they will submit their final reports when their projects are done. Life Garden, which did not submit its report, received a phone call from Staff to submit their report in early January. | Volume I Initial Review Performed | Address consistency issues for 2014 revision | B Ongoing
ii | Sector Los Angeles | Jennings, Kong | In January 2001, the FWC determined recommendations on two of the applications submitted, in the total amount of $5960. The Board approved the recommendations in April. | FWC decided on the final grant recipients in February. Grant awardees got their checks in April. | Reviewed all projects that were funded in the 2002. | Volume I Initial Review Performed | Address consistency issues for 2014 revision | B Ongoing
iii | Sector San Diego | Jennings, Wiese |  | By December 31, 2003, CEMAR or CREEC did not send a report. FWC added a requirement for the grant awardees that they return the funded money if they did not use it by the end of the year. The Board of Supervisors approved the requirement. | The previous year's grant t recipients, CEMAR and CREEC submitted their reports. | Volume I Initial Review Perforrmed | Address consistency issues for 2014 revision | B Ongoing
2 | Volume II (Section 9800) Review and Consistency | All |  |  |  | Volume II Initial Review Performed for all Sectorsfor all sectors | Address consistency issues for 2014 revision | B Ongoing
i | Coastal Access | Jennings, Haffner, Gold |  |  |  | CA info removed from ACPs and organized as stand-alone documents for ACPs 2 and 4, as pilot. Migration presented to ACs as part of Outreach Presentation in the Fall. | Remove CA info from ACPs as stand-alone documents for ACPs 1, 3, 5, 6, while finalizing format for ACPs 2,4, including OD summaries. Remove ACP Footers and Update CA database for incorporation into ERMA, using ACP 1 format. | A March 2014
ii | Economic Sites | Jennings, Kong, Ewing, Murphy, Doty |  |  |  | Murphy and Doty initiated review of economic site consistency between local plans, ACPs and ERMA. Reviewed criteria for economic sites: confirmed that D sites would be maximimzed, E sites left alone or clustered, and F sites minimized. | Murphy and Doty to continue effort to make economic sites for Local Plans, ACPs, ERMA consistent and encourage local government to verify economic sites for 2014 ACP Revision. | A March 2014
iii | GRAs versus GRPs | Jennings, Dayton, Kong, Wiese |  |  |  | Developed naming/numbering convention for document library and ACP files with Statewide GRA designations established. | Use File Naming Matrix for ACP 2014 revision files. Jennings to reorganize ACP Document Library and add files to appropriate sections. | A Ongoing June 2014
iv | GIS Layers and Diagrams | Guffy, Ewing, Jennings |  |  |  | Section 9800 - Confirmed changing site base maps from topo/nautical to aerial. GRA level map formats also made consistent. | Implement confirmed map changes, working with appropriate OSPR ESs. | A Ongoing June 2014
v | Trajectories for Discharge Scenarios | Jennings |  |  |  | Met with Sector Sf. Determined that trajectories in Section 9000 can be removed from ACP. | Review Section 9000 for Sectors LA/LB and SD. Discuss those Sectors. Confirm removal of trajectories for Sector SF with Jordan Stout | C Ongoing April 2014
vi | Eelgrass and other Natural Resource Input | Price, Schommer |  |  |  | Determined that no new eelgrass should be protected as sensitive sites (SF Only). | Update eelgrass sites with strategies designed to accomodate expansion. Sector SF only. | B Ongoing March 2014
vii | Incicdent Command Posts (ICPs) | Jennings, Kong, Wiese, Murphy, Doty |  |  |  | Determine existing efforts to identify ICPs for ACPs and encourage USCG to take ownership | Work with USCG and local government to identify ICPs for ACPs, as needed. | C Ongoing April 2014
viii | Water Intakes | Schommer, Dayton, Gold, Kong, Wiese |  |  |  | Reviewed pre-9/11 ACPs, ESIs to identify water intakes, update confidential WI database with input from stakeholders. | Create password-protected ERMA Water Intake layer (from Economic Site Layer- Category D Sites?) and add list of contacts. | C Ongoing April 2014
C. | Conduct ACP Outreach to Constituents
1 | Create ACP Outreach Presentation | Jennings, Kong, Wiese |  |  |  | Delivered presentation on 2014 Revisions to Section 9800 to Area Committees statewide, and to Statewide AC (2013) | Provide 2014 ACP Revision Schedule at Statewide AC Meeting (2014) | A February 2014
2 | Promote local government participation in ACP process | Jennings, Kong, Wiese |  |  |  | Local government outreach training conducted throughout state. | Continue local government outreach training | C Ongoing
3 | ACP ADA, Archiving and Repositories | Jennings |  |  |  | Discussed ADA compliance issues with USCG. Created File Naming Matrix for 2014 ACP revisions. | Establish better archiving capabilities (file organization). Posting of Draft ACPs to Homeport on 5/30/14 | A Ongoing May 2014
4 | Make ACP available on DVD | Jennings |  |  |  | Streamline process. Discussed with USCG | Streamline process. Continue to discuss possiblity of internal copying of CDs with USCG | B Ongoing October 2014