Incident Command System
Operations Section Chief (OPS)

- Overview

| User | The user of this job aid will be anyone who is assigned as Operations Section Chief (OPS) within the Incident Command System (ICS). Personnel should have ICS I-100 through I-300 training and position specific training as OPS for a type 1-3 incident. |
| --- | --- |
| When to Use | This job aid should be used to assist the Operations Section Chief whenever an incident has occurred that requires the Incident Command System Organization to respond. |
| Major Accomplishments | Below is a list of the major accomplishments: - Operations Section established - Resources used efficiently - Staging area established - Resources re-directed and operational - Operations brief given - Revised tactics in response to catastrophe - Evidence preserved - Access to private property obtained - Section demobilized |
| References | Below is a list of references that may be required while using this job aid: - Oil Spill Field Operations Guide (FOG) (ICS OS-420-1) - NIIMS ICS Position Manual, Operations Officer (NFES 1985) - NIIMS Task Book for Operations Section Chief (NFES 2309) - NFCG Reference Text (NFES 1960) 2309 |

Continued on Next Page

- Overview  (Cont’d)

| Materials | Ensure these materials are available to the Operations Section Chief during an incident, if not already provided in a unit or section specific support kit. |  |
| --- | --- | --- |
|  |  Field Operations Guide |  NIOSH TLV Guide |
|  |  Local telephone directory |  CHRIS Manual |
|  |  ICS Forms Catalog |  Communications Plan |
|  |  Contingency Plans |  TOMES |
|  |  Charts and maps |  CAMEO and SPEARS |
|  |  USN SUPSALV Salvor's Handbook |  Blank roster for assisting/ cooperating agency |
|  | - NOAA Shoreline Cleanup Counter-Measures Manual - National SAR Manual - Federal Response Plan - Maritime Law Enforcement Manual Vol I & II |  Pens, pencils, note paper, stapler, Post-it Notes, other office supplies |
| General Information | All radio communications to Incident Communications Center will be addressed: “(Incident Name) Communications”. Use clear text and ICS terminology (no codes) in all radio transmissions. |  |

- Initial Actions

| General Tasks | Use the job aid below to assist with initial actions to be completed by the Operations Section Chief. |  |  |
| --- | --- | --- | --- |
|  | STEP | ACTION |  |
|  | 1. | Review common responsibilities contained in ICS OS-420-1. |  |
|  | 2. | Obtain an initial brief from the Incident Commander - Size and complexity of incident - Expectations of the IC - Incident objectives - Agencies/organizations/ stakeholders involved - Incident activities/situation - Special concerns |  |
|  | 3. | Begin/maintain Unit/Activity log (ICS 214) |  |
|  | 4. | Acquire work materials from list on page 2 |  |
|  | 5. | Set up workstation |  |

- Operations Section Established

| Identify Resources | Below is a checklist for identifying and organizing resources. |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  | STEP | ACTION |  |  |  |
|  | 1. | Identify resources - Consult with Resource Unit Leader if assigned - Consult with Division/Group Supervisors and Staging Area Managers |  |  |  |
|  | 2. | Use the decision table below to evaluate span of control within the Operations Section |  |  |  |
|  |  | IF Span of Control is: | THEN: |  |  |
|  |  | Optimal (e.g., 1-5 resources assigned) | Maintain current staffing |  |  |
|  |  | Exceeded or has the potential to be exceeded | Create branches, divisions or groups as needed; assign resources |  |  |
|  |  | NOTE: Establish division boundaries if using divisions. Reasons for establishing divisions or groups - Geographic constraints Example: River, inlet, sound, bay, onshore, offshore, highway, mountains, valleys - Multi-functional operations occurring within one geographic area Example: shoreline cleanup, near shore recovery, protective booming, emergency medical services, SAR, underwater operations |  |  |  |
|  | 3. | Identify other agency and RP technical specialists needed to meet objectives Example: If shoreline protection is occurring then consider need for sensitive area specialist, historical preservation specialist, and/or equipment specialist, archeologists, and Critical Incident Stress Management (CISM) teams. |  |  |  |

Continued on Next Page

- Operations Section Established  (Cont’d)

| Identify Resources (Cont'd) | The checklist for identifying and organizing resources is continued below. |  |  |
| --- | --- | --- | --- |
|  | STEP | ACTION |  |
|  | 4. | Identify and assign resources to specific functions NOTE: These may be assigned to divisions or groups, strike teams or task forces |  |
|  | 5. | Establish communications with the field - Establish a communications schedule with branches, divisions, and group supervisors, e.g., every 4 hours check-in and pass status information. Information to pass includes: - Daily activities - Resources assigned - Resource needs - Weather conditions on site - Safety constraints - Accomplishments for inclusion into the operations brief, specified by time - Tactics revision recommendations - Assignment recommendations - Use alternative resources that are available Examples: Cell phone, VHF/UHF radio, SAT phone, computer modem, or telephone |  |

Continued on Next Page

- Operations Section Established  (Cont’d)

| Identify Resources (Cont'd) | The checklist for identifying and organizing resources is continued below. |  |  |
| --- | --- | --- | --- |
|  | STEP | ACTION |  |
|  | 6. | Determine current status of operations: - Consult with Situation Unit Leader, if assigned - Consult branches, divisions, groups, staging area managers, task forces, and strike teams Examples of information to be obtained: - Current tactics employed - Resources assigned - Resource needs - Weather conditions on site - Safety constraints - Tactical revisions recommended - Assignment recommendations |  |
|  | 7. | Establish security and accountability for tactical resources - Establish security at staging areas - Establish on-site land security for divisions or groups - Establish waterside security - Establish safety zones for waterside operations - Have the Coast Guard issue Broadcast Notice to Mariners (BNTM) - Establish security zones for events dealing with national security issues - Establish flight restrictions - Have the Federal Aviation Administration issue Notice to Airmen (NoTAM) |  |

Continued on Next Page

- Resources Used Efficiently (Cont’d)

| Tasks |  | Below is a checklist for using resources efficiently. |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | STEP | ACTION |  |  |  |  |  |
|  | 1. | Develop strategies, tactics and assignments, based on incident type and IC’s immediate objectives |  |  |  |  |  |
|  | ICS 202 Example: |  |  |  |  |  |  |
|  | Mission area example |  | Objective | Strategy | Tactic | Assignments |  |
|  | - Oil Spill |  | - Skim all free-floating oil on the Savannah River by 2000 | - Skim oil at source - Collect oil as it flows down the river before reaching staging areas | - Place OSRV down current from leaking tank ship - Deploy collection boom at Ocean Terminal slip no.1 and skim oil | Oil Skimmer Group - Use GEORGIA RESPONDER 600 ft from leaking tank ship - Deploy helo to direct skimming resources - Deploy 300’ of 18” harbor boom and deploy weir skimmer and 3 vacuum trucks to recover product |  |
|  | - Search and Rescue (SAR) |  | - Conduct search to rescue 3 potential victims 20 miles offshore at position --- by (time based on input time given by RCC) | - Surface search based on prevailing weather conditions, i.e., temperature, wave height and wind | - Parallel search or expanding square search dependant on situation, e.g., PIW, or in rafts, etc. | - Single resource; - 41436 search area B-1 |  |

- Resources Used Efficiently (cont'd)

| Tasks |  | Below is a checklist for using resources efficiently. |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | STEP | ACTION |  |  |  |  |  |  |
|  |  | ICS 202 Example (cont'd) |  |  |  |  |  |  |
|  | Mission area example | Objective | Strategy | Tactic | Assignments |  |  |  |
|  | - Hurricane Operations | - Verify Savannah River channel is safe for navigation by 2400 | - Assess ATON damage & positions - Conduct hydrographic surveys of channel | - Complete offshore areas first due to wx conditions - Complete inland surveys | - Waterways Group - (2) 21' & (1) 55'ATON vessels - (2) 35' hydrographic survey craft |  |  |  |
|  | - Maritime Law Enforcement | - Intercept/interdict drug smuggling operations on the M/V "GOTTA JOINT" based on most current intelligence | - Establish harbor surveillance at Elba Island Cut and Field's Cut | - ID each transiting vsl which fits description - Set up "picket boats" using undercover local marine resources to ID suspect vsl | - LE Task Force 3; - HH-65A - 41325 - 22354 - 20 MP boat - 22 MP boat |  |  |  |

Continued on Next Page

- Resources Used Efficiently  (Cont’d)

| Tasks | The checklist for using resources efficiently is continued below. |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  | STEP |  | ACTION |  |  |
|  | 3. | Establish immediate for next operational period tactics - Consult division/group supervisor and Strike Teams/Task Force Leaders for recommended tactics and resource needs - See major accomplishments for revised tactics if major change in situation - Use ICS 215 (Operational Planning Worksheet) to develop operational tactics for next operational period |  |  |  |
|  | 4. | Address personnel safety issues - Consult with Safety Officer if assigned - Identify the 11 common safety hazards - Slips, trips and falls - Oxygen hazards - Explosion hazards - Toxicity hazards - Radiation hazards (Ionizing and Non-Ionizing) - Electrical hazards - Noise hazards - Thermal hazards (heat and cold) - Chemical hazards - Cargo chemical agents, non-cargo - Biological hazards (virus, bacterial, fungus, parasite, or living organism that can cause disease in humans) |  |  |  |

Continued on Next Page

- Resources Used Efficiently  (Cont’d)

| Tasks | The checklist for using resources efficiently is continued below. |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | STEP |  |  | ACTION |  |  |  |  |  |  |  |
|  | 5. |  | Identify/assign resources to accomplish objectives Develop and implement emergency response plan if situation involves release of substance above the Threshold Limit Value (TLV) Use decision table below for emergency situations and time critical situations as deemed reasonable and necessary |  |  |  |  |  |  |  |  |
|  |  |  | IF Commercial Resources are |  |  | THEN Use |  |  |  |  |  |
|  |  |  | Available and adequate |  |  | Commercial first |  |  |  |  |  |
|  |  |  | UNavailable or INadequate |  |  | Government resources |  |  |  |  |  |
|  | 6. |  |  | Provide statistical information critical to the success of the operation, which is needed by controlling/directing agencies; obtain data needed from Division/Group Supervisors Example: Use the worksheet below (for oil spills) calculate the percentage of oil recovered; |  |  |  |  |  |  |  |
|  |  | Step |  |  | ACTION |  | CALCUATION |  |  |  |  |
|  |  | 1. |  |  | Enter total gallons (oil + water mixed) recovered by SKIMMERS |  | ______________gal |  |  |  |  |
|  |  | 2. |  |  | Estimate percentage of oil in oil/water mix |  | _____________% |  |  |  |  |
|  |  | 3. |  |  | Multiply Step 1 by Step 2 to determine amount of oil recovered by skimmers |  | _____________gal |  |  |  |  |
|  |  | 4. |  |  | Enter amount of oil recovered in ABSORBENTS |  | _____________gal |  |  |  |  |
|  |  | 5. |  |  | Enter amount of oil recovered by other means |  | _____________gal |  |  |  |  |
|  |  | 6. |  |  | Add Steps 3, 4, and 5 to determine total oil RECOVERED |  | _____________gal |  |  |  |  |
|  |  | 7. |  |  | Enter total amount of oil SPILLED |  | _____________gal |  |  |  |  |
|  |  | 8. |  |  | Divide Step 6 by Step 7 to determine percentage of oil recovered |  | _____________% |  |  |  |  |
|  | 7. |  |  | Provide critical statistical information to situation unit. |  |  |  |  |  |  |  |

- Staging Areas Established

| Tasks | Below is a checklist for setting up the staging areas. |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | STEP |  | ACTION |  |  |  |  |
|  | 1. |  | Establish staging area in close proximity to incident operations |  |  |  |  |
|  | 2. |  | Establish staging area away from all hazards. Use the decision table below |  |  |  |  |
|  |  | IF: |  | THEN Select a Staging Area: |  |  |  |
|  |  | Water |  | Large enough to accommodate vessel resources, i.e. shipyard for larger vessels, marinas/boat ramps for smaller vessels to provide rapid access to incident Other considerations: - Tidal conditions - Currents - Provides personnel adequate access to/from vessel |  |  |  |
|  |  | Land |  | To accommodate any size vehicle – access roads present to accommodate resources to respond to incident |  |  |  |
|  | 3. |  | Assign Staging Area Manager - Refer to Field Operations Guide, page 5-3, for Staging Area Manager responsibilities - Staging Area Managers coordinate with Resource Unit Leader |  |  |  |  |

Continued on Next Page

- Staging Areas Established  (Cont’d)

| Tasks (Cont'd) | The checklist for setting up the staging areas is continued below. |  |  |
| --- | --- | --- | --- |
|  | STEP | ACTION |  |
|  | 5. | Coordinate with property owners for possible staging area use - Consult applicable Contingency Plans - Coordinate with Logistics Section Chief for possible lease agreements - Coordinate with state or local agencies if publicly owned |  |

- Resources Redirected

| Tasks | Below is a checklist for redirecting resources. |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | STEP |  | ACTION |  |  |  |  |  |
|  | 1. |  | Analyze resource allocation within divisions and groups. Use the decision table below - Identify resources not fully utilized - Identify resource deficiencies |  |  |  |  |  |
|  |  | IF Resource Is |  | AND | AND | THEN |  |  |
|  |  | Needed |  | Available from staging |  | Redirect to deficient division or group |  |  |
|  |  |  |  | NOT available from staging |  | Order from RUL and assign |  |  |
|  |  | Surplus |  | Assigned to division or group | Potential need exists | Assign to staging |  |  |
|  |  |  |  |  | NO potential | Demobilize |  |  |
|  | 2. |  | Inform ResourceUnit Leader of resource move |  |  |  |  |  |

- Operations Brief Given

| Tasks | Below is a checklist for completing an operations brief. |  |  |
| --- | --- | --- | --- |
|  | STEP | ACTION |  |
|  | 1. | Refer to page 13-1 in the Field Operations Guide (ICS OS-420-1) or other organizational field guide ( if it which tells OPS how to conduct an operations brief) |  |
|  | 2. | Brief current response actions and last shift’s accomplishments - By Division, Group, Task Force (TF) and Strike Team (ST) - ST and TF if not assigned to a Group or Division |  |
|  | 3. | Brief objectives for next operational period |  |
|  | 4. | Provide weather information Example: sea state, wave height, wind speed/direction, precipitation, forecast/current trends |  |
|  | 5. | Brief Division, Group and Air Operation assignments - Use ICS Incident Action Plan (IAP) |  |
|  | 6. | Provide safety messages |  |
|  | 7. | Provide trajectory analysis |  |
|  | 8. | Provide communication updates |  |
|  | 9. | Provide transportation updates |  |

- Revise Tactics In Response To Catastrophe

| Tasks | Below is a checklist for revising tactics in response to a catastrophe. |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  | STEP | ACTION |  |  |  |
|  | 1. | Identify hazards |  |  |  |
|  | 2. | Form task force or group to address emergency conditions (fire, SAR, salvage, etc.) - Identify immediate strategies and tactics - Identify resource needs - Specialized equipment - Incident specific trained personnel |  |  |  |
|  | 3. | Exchange information with the Incident Commander. Use the decision table below |  |  |  |
|  |  | IF: | THEN: |  |  |
|  |  | SEPARATE incident | Meet with IC for ICS 201 brief |  |  |
|  |  | MAJOR CHANGE in incident | Brief the IC on changes as outlined in FOG, page 13 |  |  |

- Access to Private Property (oil and hazardous material spills only)

| Tasks | Below is a decision table used to access private property |  |  |  |
| --- | --- | --- | --- | --- |
|  | IF Owner is | AND Owner Can | AND Adjacent Property Is | THEN |
|  | Cooperative |  |  | - 1. Document condition of property - 2. Enter |
|  | Uncooperative | Be persuaded |  | - 1. Document condition of property - 2. Enter |
|  |  | NOT be persuaded | Available and suitable | - 1. Document condition of adjacent property - 2. Enter adjacent property |
|  |  |  | NOT available or NOT suitable | - 1. Contact local, state, federal law enforcement for escort - 2. Document condition of property - 3. Enter |

- Section/Unit Demobilized

| Tasks | Below are demobilization responsibilities applicable to all personnel assigned to this section/unit. |  |  |  |
| --- | --- | --- | --- | --- |
|  | STEP | ACTION |  |  |
|  | 1. | Evaluate need for demobilization beginning early on during the event |  |  |
|  | 2. | Provide input to the demobilization plan |  |  |
|  | 3. | Consult with Liaison Officer, Demobilization Unit Leader, and Planning Section Chief for release priorities |  |  |
|  | 4. | Receive Demobilization Plan from Demobilization Unit Leader/Planning Section Chief |  |  |
|  | 5. | Brief subordinates regarding demobilization |  |  |
|  | 6. | Supervise demobilization of unit, including storage of supplies |  |  |
|  | 7. | Coordinate with Decontamination Unit Leader (if assigned) to identify contaminated resources to be demobilized; otherwise the Operations Section Chief is responsible for decontamination of resources |  |  |
|  | 8. | Provide Supply Unit Leader with a list of supplies to be replenished |  |  |
|  | 9. | Forward all Section/Unit documentation to Documentation Unit |  |  |
|  | 10. | Complete Check-out Sheet |  |  |

- Information Exchange Matrix

| Inputs/Outputs |  | Below is an input/output matrix to assist you with obtaining information from other ICS positions and providing information to ICS positions. |  |  |
| --- | --- | --- | --- | --- |
| Meet With: | WHEN: |  | OPS OBTAINS: | OPS PROVIDES: |
| Incident Commander | Check-in brief |  | IC expectations |  |
|  | Command staff meeting |  | Response objectives (prioritized list) | Feedback on status of objectives |
|  | Planning meeting |  |  | Recommended strategy and tactics to meet objectives Completed ICS 215 |
|  | Pre-ops brief |  | Motivational remarks |  |
| Planning Section Chief | Tactics pre-planning meeting |  | Alternative strategies and tactics | Proposed strategies and tactics for next operational period Input to demobilization plan |
|  | Planning meeting |  | Proposed IAP Briefing on situation, critical/sensitive areas, resource status/availablity, weather | Branch/Division/Group boundaries/functions |
|  | IAP prep meeting |  | Completed ICS 204's | Information needed to complete ICS 204's |
| Logistics Section Chief | Tactics pre-planning meeting |  | Transportation updates Prognosis for resource availablility | Transportation needs Resource needs |
| Safety Officer | Planning meeting |  | Safety message | Brief on strategy and tactics for next operational period |
| Resource Unit Leader | Tactics pre-planning meeting |  | Resource status | Resource needs / surplus |
|  | Planning meeting |  |  | ICS 215 |
| Situation Unit Leader | Tactics pre-planning meeting |  | Weather Future projections for incident |  |
|  | Planning Meeting |  |  |  |

Continued on Next Page

- Information Exchange Matrix  (Cont’d)

| Meet With: | WHEN: | OPS OBTAINS: | OPS PROVIDES: |
| --- | --- | --- | --- |
| Division and Group Supervisors | Prior to tactics pre-planning meeting | Current response actions Shift accomplishments Ops facilities assignment update Transportation needs Communications needs Berthing, meals, rest concerns Future resource needs |  |
| Task Force Leaders |  |  |  |
| Strike Team Leaders |  |  |  |
|  |  |  | Communications plan |
|  | Pre-ops brief |  | Division/Group/Air/Strike Team/Task Force assignments |