Incident Command System
Planning Section Chief

Overview

| User | The user of this job aid will be anyone who is assigned as Planning Section Chief within the Incident Command System. Personnel assigned to this position should have a good operational background and experience with the type of incident to which they are responding. Since this is a key position in the response organization, assignment should be based on experience level versus rank. Past experience as a Situation Unit Leader and/or Resource Unit Leader is highly desirable. |
| --- | --- |
| When to Use | This job aid should be used to assist the Planning Section Chief/Deputy whenever an incident has occurred that requires the Incident Command System organization to respond. |
| Major Accomplishments | Below is a list of the major accomplishments: - Decisions on resource needs - Prepared Incident Action Plan - Approved Incident Action Plan |
| References | Below is a list of references that may be required during the use of this job aid: - Field Operations Guide (ICS OS-420-1) - NIIMS I-440 Planning Section Chief Guide - NFES Planning Section Position Manual (PSC ICS 221-1) - NIIMS Planning Section Chief Position Task Book (NFES 2331) - Incident Command System (COMDTINST 3120.14) |

Continued on Next Page

Overview  (Cont’d)

| Materials | Ensure that these materials are available to the Planning Section Chief during an incident, if not already provided in a unit or section specific support kit. |  |  |  |
| --- | --- | --- | --- | --- |
|  | - ICS Forms Catalog - Field Operations Guide | - In boxes or large envelopes - Stapler |  |  |
|  |  Local charts and maps |  Push pins |  |  |
|  |  Rulers |  3 or 6 part folders |  |  |
|  |  Mylar sheets |  2 hole punch |  |  |
|  |  Felt tip pens |  Pre-printed Mtng Agendas |  |  |
|  |  Dry erase markers (wide and thin line) |  Stack pack - ICS forms on disk |  |  |
|  | - Pencils (lead and grease) - Paper, sticky notes - Scissors |  Laptop computer with printer, software  T Cards  Position Manuals for Planning Section positions |  |  |
|  | - Notebooks (some waterproof) - ICS 213 General Msg Forms |  ICS 215 (Operational Planning Worksheet)  Other IAP forms |  |  |
|  | - White out - Masking tape |  Intercom headsets for PSC and Unit Leaders |  |  |
|  |  Easel chart |  Copy enlarger/poster printer |  |  |
| General Information | Use clear text and ICS terminology (no codes) in all radio transmissions. All radio communications to Incident Communications Center will be addressed: “(Incident Name) Communications”. |  |  |  |

Initial Actions

| General Tasks | Below are initial responsibilities for the Planning Section Chief. |  |  |
| --- | --- | --- | --- |
|  | STEP | ACTION |  |
|  | 1. | Receive assignment. |  |
|  | 2. | Upon arrival at the incident, check-in at designated check-in locations. Check-in locations may be found at: - Incident Command Post - Base or Camps - Staging Areas - Helibases |  |
|  | 3. | Obtain an initial brief from Incident Commander (IC) - Expectations of the IC - Incident objectives - Agencies/organizations/stakeholders involved - Incident activities/situation - Special concerns |  |
|  | 4. | Obtain ICS 201 from IC if this is the initial assignment of a PSC. If this is a relief or transition assignment then obtain IAP/briefing from the current PSC |  |

Continued on Next Page

Initial Actions  (Cont’d)

| General Tasks (Cont'd) | Initial responsibilities for the Planning Section Chief are continued below. |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  | STEP | ACTION |  |  |  |
|  | 5. | Review ICS 201 (pages 1-4) |  |  |  |
|  |  | ICS 201 Section (page) | Contains | Consider |  |
|  |  | Map/sketch (page 1) | Geographic scope of incident and layout of organization, divisions/groups, facilities, boundaries, resource locations | Need for changes to geographic layout of organization |  |
|  |  | Summary of current actions (page 2) | Actions taken to date | Any additional actions needed |  |
|  |  | Current organization (page 3) | Understanding of personnel assignments to date | Adequacy of current organization to meet incident needs |  |
|  |  | Resource summary (page 4) | Resources on-scene and ordered in Resource location/status | Need for resources in addition to those on scene/ordered in |  |
|  | 6. | Begin/maintain Unit Activity Log (ICS 214) |  |  |  |
|  | 7. | Acquire work materials listed on page 2 |  |  |  |
|  | 8. | Complete forms and reports required of the assigned position and send these documents to Documentation Unit at end of each operational period |  |  |  |

Decision on Resource Needs

| Assess Personnel Already Assigned to Incident | Determine optimal assignments for Incident personnel. |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
|  | STEP | ACTION |  |  |  |  |
|  | 1. | Determine assignments/status of personnel already on scene at incident |  |  |  |  |
|  |  |  | IF ICS 201 | THEN Determine from |  |  |
|  |  |  | Available | ICS 201, page 3 (Current Organization) ICS 201, page 4 (Resources Summary) |  |  |
|  |  |  | NOT available | Initial brief with IC Check-in List (ICS 211 or equivalent) Organization charts Personal observation/interview |  |  |
|  | 2. | Determine qualifications of assigned personnel |  |  |  |  |
|  |  |  | IF ICS 201 | THEN |  |  |
|  |  |  | Completed | Check resources summary for qualifications NOTE: The ICS 201 does NOT currently require that this information be recorded |  |  |
|  |  |  | NOT complete | Look at alternative sources for information - Check-in List (ICS 211, Block 15) - Unit Watch Quarter and Station Bill - Personal interview/observation |  |  |
|  | 3. | Assign on scene personnel to based on availability & qualifications as determined in Steps 1 and 2 |  |  |  |  |

Decision on Resource Needs  (Cont’d)

| Activate Planning Section Units | Use the worksheet below to calculate staffing needs for the Planning Section. |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | STEP | ACTION |  |  |  |  |  |
|  | 1. | Determine the appropriate staffing for the Planning Section using the table below: |  |  |  |  |  |
|  |  | NOTE: When ordering personnel for the Planning Section also consider the need for check-in recorders, field observers and display processors. |  |  |  |  |  |
|  |  | Position | Size of Incident (Number of Divisions) |  |  | Number Needed |  |
|  |  |  | 2 | 5 | 10 or more |  |  |
|  |  | Planning Section Chief | 1 | 1 | 1 | 1 |  |
|  |  | Deputy Planning Section Chief | 0 | 0 | 1 |  |  |
|  |  | Resource Unit Leader | 1 | 1 | 1 | 1 |  |
|  |  | Situation Unit Leader | 1 | 1 | 1 | 1 |  |
|  |  | Documentation Unit Leader | 0 | 1 | 1 | ______ |  |
|  |  | Demobilization Unit Leader | 0 | 0 | 1 | ______ |  |
|  | Total |  |  |  |  | ______ |  |
|  | 2. | Multiply the Total in Step 1 by (2) for 24 hour operations |  |  |  |  | _____ |
|  | 3. | Subtract number of personnel already assigned to Planning Section |  |  |  |  | _____ |
|  | 4. | Order remainder (number and qualifications) using ICS 213 (General Message Form); route to Logistics Section Chief |  |  |  |  | _____ |

Decision on Resource Needs  (Cont’d)

| Conduct Section Briefing | The checklist below should be completed at the BEGINNING OF EACH OPERATIONAL PERIOD. |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
|  | STEP | ACTION |  |  |  |  |
|  | 1. | Meet with Unit Leaders |  |  |  |  |
|  | 2. | Discuss status of objectives from previous operational period |  |  |  |  |
|  | 3. | Establish and post short-term objectives for upcoming operational period |  |  |  |  |
|  | 4. | Provide feedback on Unit Leader performance |  |  |  |  |
|  | 5. | Assess size of Planning Section and determine need to order/demobilize personnel |  |  |  |  |
|  | 6. | Query Unit Leaders for problems or concerns to be addressed (personnel issues, training needs, etc.) |  |  |  |  |
| Assign Technical Specialists | Technical specialists need to be properly checked-in and assigned. |  |  |  |  |  |
|  | STEP | ACTION |  |  |  |  |
|  | 1. | When a technical specialist reports to the Planning Section, determine status and assign: |  |  |  |  |
|  |  |  | IF | THEN |  |  |
|  |  |  | Properly checked-in | Assign to requestor Notify Resources Unit of status |  |  |
|  |  |  | NOT properly checked-in | Record check-in information on ICS 211 Assign to requestor Notify Resources Unit of status |  |  |
|  |  | NOTE: Track technical specialists and observe continued need for assignment during operational planning |  |  |  |  |

Incident Action Plan Prepared

| Transition from ICS 201 to IAP | The Planning Section Chief is responsible for preparing the IAP. |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
|  | STEP | ACTION |  |  |  |  |
|  | 1. Incident Action Plan This Operational Period Next Operational Period Updated Incident Briefing ICS 201 Updated Incident Briefing ICS 201 | Determine (from Incident Commander) when the transition from ICS 201 to formal Incident Action Plan will occur: |  |  |  |  |
|  |  |  | IF | THEN |  |  |
|  |  |  | ICS 201 | Update ICS 201 for next operational period NOTE: The ICS 201 can be used as the IAP for as long as the IC determines that this is appropriate |  |  |
|  |  |  | Formal IAP | Determine from IC - Length of operational periods (12 or 24 hours commonly used) - Start times for operational periods - Deadline for completion of IAP |  |  |

Continued on Next Page

Incident Action Plan Prepared  (cont’d)

| Transition from ICS 201 to IAP (Cont'd) | The checklist for preparing the IAP is continued below. |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | STEP | ACTION |  |  |  |  |  |
|  | 2. | Given the IAP completion deadline, and using the planning cycle illustrated below, work backwards to establish the IAP development schedule: |  |  |  |  |  |
|  |  |  | IF | AND Event is | THEN |  |  |
|  |  |  |  | IC/UC command objectives | X - 8 |  |  |
|  |  |  | Submission Deadline = X | Pre-planning meeting | X - 6 |  |  |
|  |  |  |  | Planning meeting | X - 3 |  |  |
|  |  |  |  | IAP preparation | X - 2 |  |  |
|  | ICS 201 Incident Briefing Command Sets Objectives Pre-planning Meeting Planning Meeting IAP Prep Ops Briefing IAP Approval & Distribution Execution & Evaluation IAP Submission Deadline X-3 X-6 X-8 2 hours 2 hours 60minutes 3 hours 2 hours Start of Shift X-2 | Note: This IAP development schedule should be used to negotiate the submission deadline for the first IAP. The PSC is responsible for ensuring the IC understands the development cycle and the time needed to produce the IAP. Note: These times are approximated for the first cycle and may vary significantly based on incident complexity and length of the operational period. |  |  |  |  |  |

Continued on Next Page

Incident Action Plan Prepared  (cont’d)

| Facilitate Meetings | The Planning Section Chief serves as the facilitator for several key meetings during each operational cycle. |  |  |
| --- | --- | --- | --- |
|  | STEP | ACTION |  |
|  | 1. | Based on times determined in previous steps, instruct the Situation Unit Leader to prepare ICS 230 (Daily Meeting Schedule) NOTE: These are not the only meetings/events that need to be included on the ICS 230; ensure the SUL also includes press briefs, VIP visits, IC updates, command staff meetings and other significant events during the operational period. |  |
|  | 2. | Ensure completed ICS 230 is posted on Situation Status display and distributed to all Command Staff, Section Chiefs, Division/Group Supervisors and appropriate Unit Leaders |  |
|  | 3. | Send reminders to meeting attendees 15-30 minutes before meeting to ensure prompt attendance NOTE: This can be done via ICS 213, email, messenger, announcement or any other method that is effective at getting the word out. |  |
|  | 4. | At designated time, facilitate each meeting to maintain schedule, cover all required aspects and produce expected deliverables. Ensure presenters are prepared to cover their portion of the meeting agenda. Determine the need for and ensure attendance of Technical Specialists if necessary. See IF/THEN table on the next pages NOTE: Agendas can be preprinted in ICS 231 (Meeting Description) and used for various meetings. |  |

Continued on Next Page

Incident Action Plan Prepared  (cont’d)

| Facilitate Meetings (cont’d) |  | The meeting facilitation job aid continues below. |  |  |  |
| --- | --- | --- | --- | --- | --- |
| IF Meeting Is | THEN |  |  |  |  |
|  | Attendees Are |  | Agenda Is | Presenter Is | Deliverables Are |
| Pre-Planning (Tactics) | PSC OPS RUL LSC SO |  | Objectives for the next operational period (clearly stated and attainable with the resources available, yet flexible enough to allow OPS to choose tactics) | OPS | Primary strategies |
|  |  |  | Strategies (primary and alternatives) | OPS with PSC | Alternative strategies |
|  |  |  | Prepare a draft of ICS 215 to identify resources that should be ordered through LSC. This process can be completed by OPS and RUL after the meeting adjourns, with RUL preparing an enlarged ICS 215 for the Planning Meeting | RUL | Draft ICS 215 (Operational Planning Worksheet) |
| Planning | IC IO LO SO OPS PSC LSC FSC RUL SUL Air Ops Technical Specialists (as needed) |  | Incident objectives/policy issues | IC/UC |  |
|  |  |  | Briefing of situation, critical and sensitive areas, weather/sea forecast, resource status/availability | PSC with SUL, RUL |  |
|  |  |  | Primary and alternative strategies to meet objectives Designate Branch, Division, Group boundaries and functions as appropriate, using maps and ICS 215 | OPS with PSC, LSC |  |

Continued on Next Page

Incident Action Plan Prepared  (cont’d)

| Facilitate Meetings (cont’d) |  | The meeting facilitation job aid continues below. |  |  |  |
| --- | --- | --- | --- | --- | --- |
| IF Meeting Is | THEN |  |  |  |  |
|  | Attendees Are |  | Agenda Is | Person Tasked | Deliverables Are |
| Planning (cont’d) |  |  | Specify tactics for each Division, note limitations | OPS with SUL |  |
|  |  |  | Specify resources needed by Division/Groups | OPS with PSC, LSC |  |
|  |  |  | Specify operations facilities and reporting locations – plot on map | OPS with LSC |  |
|  |  |  | Develop resources, support and overhead orders | PSC, LSC |  |
|  |  |  | Financial concerns/reports | FSC |  |
|  |  |  | Communications, traffic, safety, medical, and other support | LSC with PSC |  |
|  |  |  | Contributing organization/agency considerations regarding work plan | LO |  |
|  |  |  | Safety considerations regarding work plan | SO |  |
|  |  |  | Media considerations regarding work plan | IO |  |
|  |  |  | Finalize/approve ICS-215s for next operational period | IC/UC | Final ICS 215 Conceptual approval of IAP with input from all organizational elements |

Continued on Next Page

Incident Action Plan Prepared  (cont’d)

| Facilitate Meetings (cont’d) |  | The meeting facilitation job aid continues below. |  |  |  |
| --- | --- | --- | --- | --- | --- |
| IF Meeting Is | THEN |  |  |  |  |
|  | Attendees Are |  | Agenda Is | Person Tasked | Deliverables Are |
| IAP Prep NOTE: This is not a formal meeting – the tasking required to complete this step can be handed out immediately following the Planning Meeting | LSC PSC OPS RUL SUL SO |  | Establish deadlines for following: Incident Objectives (ICS 202) Organization List/Chart (ICS 203 or 207 Assignment List (ICS 204) | RUL (w/OPS assist) | ICS 202, ICS 203/207 ICS 204 |
|  |  |  | Communications Plan (ICS 205) | LSC | ICS 205/206 |
|  |  |  | Medical Plan (ICS 206) |  |  |
|  |  |  | Traffic Plan |  | Traffic Plan |
|  |  |  | Incident map | SUL | Incident maps ICS-OS-209 ICS-OS-232 |
|  |  |  | Operational Components (use as pertinent): |  |  |
|  |  |  | Air Operations Summary (ICS 220) | OPS | ICS 220 |
|  |  |  | Daily Safety Message | SO | Daily Safety Message |
|  |  |  | Demobilization Plan | PSC | Demobilization Plan |

Continued on Next Page

Incident Action Plan Prepared  (cont’d)

| Facilitate Meetings (cont’d) |  | The meeting facilitation job aid continues below. |  |  |  |
| --- | --- | --- | --- | --- | --- |
| IF Meeting Is | THEN |  |  |  |  |
|  | Attendees Are |  | Agenda Is | Person Tasked | Deliverables Are |
| Ops (shift) Brief | IC IO LO SO OPS PSC LSC FSC Div/Group Supervisors Task Force Leaders Strike Team Leaders Unit Leaders |  | Current response actions and last shift’s accomplishments Review of IC/UC objectives, Review changes to IAP Division/Group and air operations assignments Weather and sea conditions forecast Trajectory analysis Transport, communications, supply updates Safety issues Financial report Media report Contributing organization/ agency reports/concerns | PSC OPS | Convey IAP objectives and assignments to oncoming shift |
|  |  |  |  | SUL |  |
|  |  |  |  | LSC |  |
|  |  |  |  | SO |  |
|  |  |  |  | FSC IO LO |  |

NOTE: If the incident is spread out over a large geographic area consider conducting the shift briefs in the vicinity of the actual work areas. The Division/Group Supervisors would carry out these shift briefs.

NOTE: Meeting occurs approximately 1 hour prior to start of each shift.

Incident Action Plan Prepared  (cont’d)

| Evaluate Alternative Strategies | The Planning Section Chief is responsible for developing alternatives to proposed strategies. |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | STEP | ACTION |  |  |  |  |  |
|  | 1. | Determine alternate plan(s) for each primary strategy proposed by OPS during the pre-planning meeting |  |  |  |  |  |
|  | 2. | Determine if alternate plans are precluded by any policy, regulation or other incident specific constraint |  |  |  |  |  |
|  |  |  | IF Alternate Strategy | AND | THEN |  |  |
|  |  |  | NOT feasible |  | Present only primary plan at planning meeting |  |  |
|  |  |  | Feasible | Precluded by constraints |  |  |  |
|  |  |  |  | NOT precluded by constraints | Present at planning meeting as alternative |  |  |
|  | 3. | For each alternative strategy determine: - Resources needed to execute - Resource availability - Cost |  |  |  |  |  |
|  | 4. | Be prepared to present and discuss pros/cons of alternate strategies at planning meeting |  |  |  |  |  |
| Prepare the IAP | Use the checklist below to properly prepare and assemble the IAP. |  |  |  |  |  |  |
|  | STEP | ACTION |  |  |  |  |  |
|  | 1. | At conclusion of IAP prep meeting ensure assignments/expectations are clear |  |  |  |  |  |
|  | 2. | Instruct those responsible for developing portions of the IAP to provide advance notice if deadlines will not be met |  |  |  |  |  |

Continued on Next Page

Incident Action Plan Prepared  (cont’d)

| Prepare the IAP (cont’d) | The IAP preparation checklist is continued below. |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | STEP | ACTION |  |  |  |  |  |
|  | 3. | Ensure duplication services available/adequate |  |  |  |  |  |
|  | 4. | Assemble forms for IAP |  |  |  |  |  |
|  |  | Form # (Name) | Prepared By | Draft | Final |  |  |
|  |  | IAP Cover | SUL |  |  |  |  |
|  |  | ICS 202 (Response Objectives) | PSC or IC |  |  |  |  |
|  |  | ICS 203 (Organization Assignments) | RUL |  |  |  |  |
|  |  | ICS 204 (Division/Group Assignment) | OPS/RUL |  |  |  |  |
|  |  | ICS 205 (Communications Plan) | Comms Unit Leader |  |  |  |  |
|  |  | ICS 206 (Medical Plan) | Medical Unit Leader |  |  |  |  |
|  |  | OS 232 (Resources at Risk) | SUL |  |  |  |  |
|  |  | ICS-OS-209 | SUL/RUL |  |  |  |  |
|  |  | ICS 220 | OPS |  |  |  |  |
|  |  | Daily Safety Message | Safety Officer |  |  |  |  |
|  |  | Traffic Plan* | Ground Support Unit Leader |  |  |  |  |
|  |  | Incident map(s) | SUL |  |  |  |  |
|  |  | Demobilization Plan* | Demob Unit Leader |  |  |  |  |
|  |  | *As necessary |  |  |  |  |  |

Continued on Next Page

Incident Action Plan Prepared  (cont’d)

| Prepare the IAP (cont’d) | The IAP preparation checklist is continued below. |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
|  | STEP | ACTION |  |  |  |  |
|  | 5. | Proofread IAP, ensure forms complete and signed by originator |  |  |  |  |
|  | 6. | Present to IC/UC for final approval/signature |  |  |  |  |
|  | 7. | Duplicate as needed |  |  |  |  |
|  | 8. | Route signed original to DUL |  |  |  |  |
|  | 9. | Have DUL distribute as needed |  |  |  |  |
| Assemble Task Forces and Strike Teams PageAssemble Task Forces and Strike Teams at Incident | Task Forces and Strike Teams are organizational tools that help the ICS effectively manage large groups of response personnel. |  |  |  |  |  |
|  | STEP | ACTION |  |  |  |  |
|  | 1. | Determine need for Task Force/Strike Team |  |  |  |  |
|  |  |  | IF Need is for | THEN Assemble as |  |  |
|  |  |  | Group of resources with SAME type/kind | Strike Team |  |  |
|  |  |  | Group of resources with DIFFERENT type/kind | Task Force |  |  |
|  |  | NOTE: Task Forces are much more common in Coast Guard operations |  |  |  |  |
|  | 2. | Identify and group appropriate resources |  |  |  |  |
|  | 3. | Assign a Task Force/Strike Team Leader |  |  |  |  |
|  | 4. | Provide Task Force/Strike Team with comms |  |  |  |  |
|  | 5. | Designate assembly area/time |  |  |  |  |
|  | 6. | Assign via ICS 204 |  |  |  |  |
|  | 7. | Have RUL track grouped resources as Task Force/Strike Team |  |  |  |  |

Approved Incident Action Plan

| Order Appropriate Resources | In order to ensure the availability of resources for operations beyond the next operational period, the Planning Section Chief must work closely with the Operations Section Chief to anticipate resource needs. NOTE: Pre-planning and planning meetings will produce a list of resources required for the chosen objectives, strategies and tactics during the next operational period. |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | STEP | ACTION |  |  |  |  |  |
|  | 1. |  |  |  |  |  |  |
|  |  |  | IF Anticipated Operation Will Occur | AND They | THEN |  |  |
|  |  |  | During next operational period |  | Resource needs covered by ICS 215 |  |  |
|  |  |  | Beyond next operational period | Are similar in scope and complexity to current operation | Resources are likely to already be on scene |  |  |
|  |  |  |  | Go beyond scope and complexity of current operations | PSC and OPS should ID resources needed to conduct anticipated operations |  |  |
|  | 2. | Order necessary resources to arrive in time for anticipated operations. |  |  |  |  |  |

Approved Incident Action Plan  (cont’d)

| Advise Command & General Staff | The Planning Section Chief is responsible for keeping the IC/UC staff informed about incident status changes. |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | STEP | ACTION |  |  |  |  |  |
|  | 1. | Identify changes in incident status from field reports |  |  |  |  |  |
|  | 2. | Determine if changes are significant: |  |  |  |  |  |
|  |  |  | IF Status Change | THEN Change | Brief |  |  |
|  |  |  | Does not require a change in operational period objectives/ strategies | Probably NOT significant | At next planning meeting |  |  |
|  |  |  | May require change in operational period objectives/ strategies | Significant | Immediately |  |  |
|  | 3. | Notify command and general staff of ALL significant changes NOTE: Make notifications via quickest method (radio, phone, fax, messenger) |  |  |  |  |  |
| Provide Status Reports to Requesters | The Planning Section may be tasked to provide specific information regarding the incident to various requestors. |  |  |  |  |  |  |
|  | STEP | ACTION |  |  |  |  |  |
|  | 1. | Receive request for incident information |  |  |  |  |  |

Continued on Next Page

Approved Incident Action Plan  (cont’d)

| Provide Status Reports to Requesters (cont’d) | The checklist used to provide information to various requestors is continued below. |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | STEP | ACTION |  |  |  |  |  |
|  | 2. | Determine if information is available via the Situation Unit |  |  |  |  |  |
|  |  | IF Situation Unit |  |  | THEN |  |  |
|  |  | Maintains information |  |  | Task SUL to provide |  |  |
|  |  | Does NOT have requested information |  |  | - Determine best source - Obtain information/task source to provide |  |  |
| Recommend Release of Resources | From early in the incident response, the Planning Section Chief must be alert for excess resources that can be reassigned or demobilized. |  |  |  |  |  |  |
|  | STEP | ACTION |  |  |  |  |  |
|  | 1. | Identify excess resources via ICS 215 process or feedback from the field. NOTE: If resource is a Task Force or Strike Team, disassemble into single resources before proceeding to Step 2 |  |  |  |  |  |
|  | 2. | Determine if resources are needed elsewhere at the incident |  |  |  |  |  |
|  |  |  | IF Resources | THEN |  |  |  |
|  |  |  | Needed elsewhere at incident | PSC and OPS reassign and notify RUL of status change |  |  |  |
|  |  |  | Not needed at incident | Place on list of resources proposed for demobilization |  |  |  |
|  | 3. | Present list of resources proposed for demobilization to IC/UC |  |  |  |  |  |

Continued on Next Page

Approved Incident Action Plan  (cont’d)

| Recommend Release of Resources (Cont'd) | The checklist used to demobilize excess resources is continued below. |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
|  | STEP | ACTION |  |  |  |  |
|  | 4. | Demobilize resources that IC/UC approves for release |  |  |  |  |
|  |  |  | IF Resource | THEN |  |  |
|  |  |  | Approved for demobilization | Demobilize in accordance with approved demobilization plan |  |  |
|  |  |  | NOT approved for demobilization | Determine reason Keep at incident Notify RUL of status |  |  |
| Develop General Plan | The General Plan is used to generate a proposed timeline for the overall response. It can be used to make resource decisions, estimate costs for the response and manage expectations both in and outside of the response organization. |  |  |  |  |  |
|  | STEP | ACTION |  |  |  |  |
|  | 1. | Estimate time-frame for response |  |  |  |  |
|  | 2. | Determine if General Plan is feasible |  |  |  |  |
|  |  |  | IF Response Time-Frame Is | THEN General Plan Is |  |  |
|  |  |  | 7 days or less | NOT feasible |  |  |
|  |  |  | 8-14 days | CAN be used |  |  |
|  |  |  | More than 14 days | SHOULD be used |  |  |
|  | 3. | Develop General Plan if indicated by the above or required by IC/UC |  |  |  |  |

Continued on Next Page

Approved Incident Action Plan  (cont’d)

| Develop General Plan (cont’d) | The checklist for developing the General Plan is continued below. |  |  |
| --- | --- | --- | --- |
|  | STEP | ACTION |  |
|  | 4. | Assign a Detailed Incident Assessment Team (DIAT) to assemble information needed for the General Plan NOTE: This team is typically made up of representatives from operations and planning that have incident specific experience |  |
|  | 5. | Draft the General Plan in accordance with the instructions in the ICS Forms Catalog |  |
|  | 6. | Submit to IC/UC for approval |  |
|  | 7. | Distribute copies of approved plan to IC/UC, Command and General Staff |  |
|  | 8. | Have DIAT update plan every 3-4 days, resubmit for approval, and distribute |  |
| Section/Unit Demobilized Tasks | Below are demobilization responsibilities applicable to supervisory personnel assigned to this section/unit. |  |  |
|  | STEP | ACTION |  |
|  | 1. | Provide input to the Demobilization Unit Leader who develops the Demob Plan |  |
|  | 2. | Brief subordinates regarding demobilization |  |
|  | 3. | Debrief appropriate personnel prior to departing incident  Incident Commander  Logistics Section Chief |  |
|  | 4. | Supervise demobilization of section, including storage of supplies |  |
|  | 5. | Provide Supply Unit Leader with a list of supplies to be replenished |  |
|  | 6. | Forward all Section documentation to Documentation Unit |  |
|  | 7. | Complete Check-out Sheet |  |

Information Exchange Matrix

Information Exchange Matrix

| Inputs/Outputs |  | Below is an input/output matrix to assist the Planning Section Chief with obtaining information from other ICS positions and providing information to ICS positions. |  |  |
| --- | --- | --- | --- | --- |
| MEET With | WHEN |  | PSC OBTAINS | PSC PROVIDES |
| Incident Commander | Initial incident brief |  | ICS 201 or verbal brief on incident status | Feedback on initial response activity/organization |
|  | During initial response phase |  | Operational Periods Deadline for initial IAP submission IC/UC objectives | Feedback on operational period and IAP deadline Feedback on objectives |
|  | Planning meeting |  | Restatement of response objectives | Proposed IAP Briefing on situation, critical/sensitive areas, resource status/availability, weather |
|  | IAP approval process |  | Approved IAP | IAP for approval |
| Safety Officer | Planning meeting |  | Concerns regarding safety issues in IAP | Proposed IAP Briefing on situation, critical/sensitive areas, resource status/availability, weather |
|  | IAP prep process |  | Safety messages | Feedback on safety messages Update on response operations |
| Liaison Officer | Planning meeting |  | Concerns regarding liaison issues | Proposed IAP Briefing on situation, critical/sensitive areas, resource status/availability, weather |
| Information Officer | During initial response phase |  | Estimated time of press briefings | Completed ICS 230 (Meeting Schedule) |
|  | Planning meetings |  | Media concerns considerations | Proposed IAP Briefing on situation, critical/sensitive areas, resource status/availability, weather |

Continued on Next Page

Information Exchange Matrix (continued)

| MEET With | WHEN | PSC OBTAINS | PSC PROVIDES |
| --- | --- | --- | --- |
| Operations Section Chief | Pre-planning meeting | Strategy/tactics Resource needs | Input on alternative strategies |
|  | Planning meeting | Primary/alternative strategies Branch/Division and Group boundaries/functions Tactics Resource needs Ops facilities | Proposed IAP Briefing on situation, critical/sensitive areas, resource status/availability, weather |
|  | IAP prep meeting | Information to complete ICS 204’s ICS 220 (Air Operations Summary) | Completed ICS 204’s Feedback on IAP submissions |
| Logistics Section Chief | During initial response phase | Confirmation of staffing order | ICS 213 with resource order to staff Planning Section |
|  | Planning meeting | Feedback on resource availability Facility details Support plan input | Proposed IAP Briefing on situation, critical/sensitive areas, resource status/availability, weather |
|  | IAP prep | ICS 205 ICS 206 Support plans (Traffic Plan) | Feedback on IAP submissions |
| Finance/ Administration Section Chief | Planning meeting | Update on finance concerns | Proposed IAP Briefing on situation, critical/sensitive areas, resource status/availability, weather |
|  | Shift brief | Financial Report | Review of IC/UC objectives |
| Technical Specialists | As they report in | Check-in information | Assignment Brief on incident status |